## 00 Read Me
STL Lucinda Access Methodology - Productivity and Cost Model
Commercial in confidence ¦ All fees and costs AUD ex GST unless stated otherwise
Document ID | ED-018-2026-07
Revision | A - internal working model
Date | 20 August 2026
Prepared by | Endura Decommissioning (Van Iersel Projects Pty Ltd)
Purpose | Formula-driven comparison of the current scaffold methodology and the candidate reusable marine access system. Supports Stage 1 methodology, programme, cost and risk assessment.
Assurance status | Concept-stage working model. Not for construction, procurement or cost commitment.
Key rule | Claimed payment-stage equivalents are not treated as completed bents. Proposed rates are QA-closed bents/week only where the full cycle is represented.
Input colour | Pale yellow = user/supplier input; green = project evidence; blue = formula; red = missing/gating input.
Current limitation | Headstock containment, below-LAT jacket installation, full coating elapsed holds, supplier platform configuration, JUB staging and current bent register remain open.
Required stress test | 227 bents / 60 nominal production weeks = 3.783 QA-closed bents/week. This is a conservative whole-scope stress test, not confirmation that all 227 are priority repairs.
Recommended use | Use the model to test access sets, weld crews, approval strategy, shifts and verified supplier rates. Do not quote a total cost while red/TBC inputs remain.
Repository rate extraction | 0 currency/rate candidate lines were extracted to 06 Rate Register. Every candidate remains Use in model = N until checked against the original GGC/supplier source.

## 01 Source Manifest
Source Manifest and Extraction Coverage
No. | Repository path | Type | Size (MB) | SHA-256 | Extraction status | Pages/sheets | Text chars | Review relevance | Current/superseded | Notes

## 02 Proposal Compliance
Stage 1 Proposal Deliverable Compliance Matrix
ID | Proposal commitment / required output | Current package treatment | Evidence / workbook sheet | Status | Action before STL issue
D01 | Review project information, contract, drawings, reports, programme and current progress | Source manifest and baseline review | 01 Source Manifest; 03 Current Baseline; 04 Current Schedule | Covered | Maintain controlled source register and close unreadable/native schedule limitations.
D02 | Define and screen access methodology options | Current scaffold, reusable marine access and hybrid/special-bent pathways | Methodology Sections 4-5; 12 Comparison | Covered | Add formal weighted option-screening table after supplier input.
D03 | Define working configuration and equipment make-up | Two long-face platforms, traversing decks, half-shell containment, access towers, JUB and workboat | 05 Proposed WBS; 08 Productivity | Concept defined | Close platform, winch, traversing deck and containment supplier data.
D04 | Define deployment and bent-to-bent relocation | Detailed mobilisation, pre-rig, float-in, lift, service connection, lower and tow sequence | 05 Proposed WBS; 10 Programme | Covered conceptually | Validate by timed trial and marine operations plan.
D05 | Assess tide, weather and operability | Activity-specific weather/tide gates and residual availability input | 08 Productivity; 10 Programme; 13 Risks | Partial | Build dated metocean/ship-call calendar from STL records.
D06 | Develop containment and waste-recovery approach | Pile half-shell and headstock enclosure gate, negative pressure, abrasive/wash-water recovery | 05 Proposed WBS; 13 Risks | Partial | Supplier design and environmental acceptance criteria required.
D07 | Define materials, waste and crew logistics | JUB service base, water logistics, crew by road, access towers, rescue craft | 05 Proposed WBS; 07 Cost Build-Up | Covered conceptually | Resource-load JUB, workboats, fuel, waste and accommodation.
D08 | Assess structural interfaces and temporary loading | Hang-off points, sliding clamps, platform states, traversing deck and containment interfaces | 13 Risks & RFIs | Open gate | RPEQ temporary-works design and independent check required.
D09 | Define cyclone, wet-season and ship-call response | Full seasonal demob, two-day make-safe, fleet recovery and refuge requirements | 10 Programme; 13 Risks | Partial | Time and resource-load recovery with selected fleet/JUB.
D10 | Compare productivity, programme, cost and risk with current method | Formula-driven baseline and scenarios; cost build-up and comparison | 03, 07, 08, 09, 10, 11, 12 | Covered with gaps | Close supplier rates and remaining bent register.
D11 | Undertake supplier and contractor market soundings | GGC/Hansen platform data, JUB candidates, raw rate register | 06 Rate Register; 13 Risks | In progress | Obtain written GGC quote, containment proposal and JUB availability/rates.
D12 | Facilitate options workshop with STL | Decision and gate list prepared | 13 Risks & RFIs | Pending | Hold workshop after draft issue.
D13 | Issue final report with recommended methodology and implementation roadmap | Companion detailed report and roadmap | DOCX report; 10 Programme | Draft prepared | Update after workshop and market sounding.

## 03 Current Baseline
Current AAB Methodology - Progress and Cycle Baseline
Stage | Claimed quantity Mar-Jul 2026 | Unit | Period weeks | Calculated rate/week | Best month | Verification note
Provision of safe access | 7.9 | bent equivalent | 21.9 |  | 3.2 | Payment-stage equivalent, not completed bent
Clean, inspect, UT and weld determination | 9 | bent equivalent | 21.9 |  | 5 | Payment-stage equivalent
Abrasive blast and coating application | 7 | bent equivalent | 21.9 |  | 3.5 | Payment-stage equivalent
Denso / petrolatum jacket installation | 12 | pile equivalent | 21.9 |  | 7.3 | Pile equivalent
Weld preparation and welding | 473.025 | lm | 21.9 |  | 202.0 lm in Jun | 183.86 lm at 8 mm + 289.165 lm at 10 mm
Current cycle activity | Low days | High days | Central days | Character | Source / limitation
Scaffold erection and encapsulation | 2 | 3 | 2.5 | Access handling | Contract programme / validated screenshots; native logic requires planner confirmation
High pressure wash, inspection, UT | 1 | 1 | 1 | Productive | Contract programme / validated screenshots; native logic requires planner confirmation
Weld repairs | 2 | 7 | 4.5 | Productive, variable | Contract programme / validated screenshots; native logic requires planner confirmation
Repair approval hold | 3 | 3 | 3 | Waiting | Contract programme / validated screenshots; native logic requires planner confirmation
Abrasive blast and two coats | 3 | 4 | 3.5 | Productive | Contract programme / validated screenshots; native logic requires planner confirmation
Pile jacket installation | 0 | 2 | 1 | Tide limited | Contract programme / validated screenshots; native logic requires planner confirmation
Scaffold strip and relocation | 1 | 2 | 1.5 | Access handling | Contract programme / validated screenshots; native logic requires planner confirmation
Representative cycle subtotal (excl Sundays/float)
Programme typical elapsed basis |  |  | 15 |  | Programme screenshots indicate approximately 14-15 calendar days; earlier stress allowance used 16 days.
Current contract access basis (firm scope) | 9275472.36 | AUD ex GST |  |  | Historical contract access basis, not remaining avoidable cost. Reconcile to current certified claims before commercial use.
Access basis per firm bent |  | AUD/bent

## 04 Current Schedule
Current Contractor Programme - Native and Screenshot Review
Field | Value | Assurance status | Comment
Native MPP file | AAB Program (June 26).mpp | Supplied | Native file inventoried; task extraction included below if available.
Programme typical bent cycle | 14-15 calendar days | Cross-checked | Matches supplied programme screenshots; do not relabel as 16 working days.
Scaffold sets physically reported | 4 sets | Project evidence | Do not infer access inventory from total WIP.
Peak bents concurrently in progress | Up to 9 | Programme observation | WIP is not the same as nine scaffold sets.
Planned production order | Approximately 2 bents/week | Client/programme basis | Confirm against final baseline and current reforecast.
Native critical path | Not independently verified | Clearance limitation | Task links/calendars/constraints/float need planner-issued export.
UID | ID | Task name | Duration | Start | Finish | Actual start | Actual finish | % complete | Critical | Summary | Total slack
NOT EXTRACTED |  | Native MPP task table unavailable to this build; use screenshot-validated summary above.

## 05 Proposed WBS
Proposed Marine Access Methodology - Detailed Activity Library
WBS | Phase | Activity | Workfront / crew | Unit | Qty per typical bent | Active shifts | Elapsed hold days | Occupies access set | Can overlap ahead | Basis class | Source / verification | Cost code
1.1 | Engineering | Bathymetric and seabed survey | Survey contractor | campaign | 1 |  |  | No | Yes | Open input | STL RFI / supplier requirements | ENG-SURV
1.2 | Engineering | Temporary works design: hang-off, sliding clamps, platforms and traversing decks | RPEQ/TW engineer | campaign | 1 |  |  | No | Yes | Open input | Supplier data required | ENG-TW
1.3 | Engineering | Containment design and environmental acceptance | Containment supplier / HSE | campaign | 1 |  |  | No | Yes | Open input | Supplier design required | ENG-CONT
1.4 | Engineering | Marine operations plan, SIMOPS, rescue, ship and cyclone response | Marine engineer | campaign | 1 |  |  | No | Yes | Open input | Stage 1 deliverable | ENG-MAR
2.1 | Mobilisation | Transport and assemble modular platforms | GGC / rigging crew | access set | 1 |  |  | No | Yes | Supplier input | GGC rates and Hansen drawings | MOB-PLAT
2.2 | Mobilisation | Install winches, travelling supports and controls | GGC / electricians / riggers | access set | 1 |  |  | No | Yes | Supplier input | GGC written confirmation required | MOB-WINCH
2.3 | Mobilisation | Assemble traversing decks and containment halves | Access / containment crew | access set | 1 |  |  | No | Yes | Supplier input | Supplier design required | MOB-CONT
2.4 | Mobilisation | Proof load, function test and rescue drill | TW engineer / marine crew | access set | 1 |  |  | No | Yes | Required gate | Before first use | MOB-TEST
3.1 | Advance rigging | Install/advance hang-off and clamp package at next bent | Rigging crew | bent | 1 | 0.4 | 0 | No | Yes | Engineering assumption | 4 h share in relocation model | REL-RIG
3.2 | Relocation | Disconnect services and lower platform pair | Platform crew | bent | 1 | 0.1 | 0 | Yes | No | Engineering assumption | 1 h | REL-LOWER
3.3 | Relocation | Tow platform pair to next bent | Workboat / platform crew | bent | 1 | 0.2 | 0 | Yes | No | Engineering assumption | 2 h | REL-TOW
3.4 | Relocation | Position, hook-on, lift, level and restrain | Platform crew / workboat | bent | 1 | 0.2 | 0 | Yes | No | Engineering assumption | 2 h | REL-LIFT
3.5 | Relocation | Move and secure access tower | JUB crane / riggers | bent | 1 | 0.1 | 0 | Yes | No | Engineering assumption | 1 h | REL-TOWER
3.6 | Relocation | Install traversing decks, services and commissioning checks | Platform crew | bent | 1 | 0.1 | 0 | Yes | No | Engineering assumption | 1 h | REL-SERVICE
4.1 | Diagnostic | Remove existing wrapping, wash, inspect and UT | Survey / inspection crew | bent | 1 | 1 | 0 | Yes | No | Project/programme basis | Inspection front | DIAG-INSP
4.2 | Diagnostic | Install half-shell and diagnostic blast both upper pile bands | Blast crew | 27-29 m2 | 1 | 1 | 0 | Yes | No | Engineering assumption | One shift conservative allowance incl moves/QA | DIAG-BLAST
4.3 | Diagnostic | Headstock diagnostic preparation and mark-up | Blast / inspection crew | bent | 1 |  |  | Yes | No | NOT MODELLED | Headstock enclosure method required | DIAG-HEAD
4.4 | Diagnostic | Mark-up both piles and headstock; prepare bent repair package | Engineer / inspector | bent | 1 | 0.5 | 0 | Yes | No | Engineering assumption | Bent-level submission basis requires confirmation | DIAG-MARK
4.5 | Approval | Bent-level repair design review and approval hold | Reviewing engineer / STL | bent | 1 | 0 | 3 | Yes | Yes elsewhere | Programme basis / assumption | One hold assumes full bent exposed first | APP-HOLD
5.1 | Repair | Repair steel detail, prefabrication and delivery | Fabrication crew | lm | 53 | 0 | 0 | No | Yes | Client payment quantity | Prefabricate from approved package | REP-FAB
5.2 | Repair | Pile 1 fit-up, welding, NDT and rectification | Weld crews | lm | 26.5 |  | 0 | Yes | No | Sensitivity | 2 crews x 6 accepted lm/crew-shift base | REP-WELD
5.3 | Repair | Pile 1 post-weld preparation | Blast/prep crew | pile | 1 | 0.25 | 0 | Yes | No | Engineering assumption | To verify at trial | REP-PREP
5.4 | Coating | Pile 1 coat 1, stripe coats, wash/dry, coat 2 and QA | Coating crew | pile | 1 | 0.75 |  | Yes | Limited | NOT FULLY MODELLED | Active work only; elapsed recoat hold requires dated work lot | COAT-P1
5.5 | Jackets | Pile 1 petrolatum jacket above LAT | Jacket crew | pile | 1 | 0.5 | 0 | Yes | No | Engineering assumption | Timed trial required | JKT-P1
5.6 | Jackets | Pile 1 jacket below LAT and lower termination | Marine/jacket crew | pile | 1 |  |  | Yes | No | NOT MODELLED | Manufacturer/marine method required | JKT-SUB
5.7 | Repair | Repeat repair, coating and jacket sequence on pile 2 | All trade crews | pile | 1 |  |  | Yes | No | Formula / concept | Same platform remains at bent | REP-P2
5.8 | Headstock | Headstock containment, repair, coating, gallery feet and keeper-angle interfaces | Multi-trade | bent | 1 |  |  | Yes | No | NOT MODELLED | Bent-family design required | HEAD-WORK
6.1 | Closeout | Containment clean-out, final QA, records, rework and bent release | QA / all trades | bent | 1 |  |  | Yes | No | NOT MODELLED | Trial and ITP required | QA-CLOSE
7.1 | Seasonal | Ship-call make-safe and restart | Marine / all crews | event | 1 |  |  | Varies | No | Calendar event | 2-day notice basis; exact scope to define | OPS-SHIP
7.2 | Seasonal | Wet-season full demobilisation and remobilisation | All marine spread | season | 1 |  |  | No | No | Client requirement | Dec-Mar basis | OPS-SEASON
7.3 | Seasonal | Cyclone fleet recovery to refuge and reinstatement | Marine spread | event | 1 |  |  | No | No | Required gate | Timed recovery plan required | OPS-CYCLONE

## 06 Rate Register
Supplier, Labour and Plant Rate Register
Rate ID | Category | Description / source context | Amount | Currency | Rate unit | Source file | Source line | Use in model? | Confidence | Notes
R001 | Current access | Contract access basis for firm scope | 9275472.36 | AUD | lump sum | AAB contract/assurance calculation | n/a | N | Verified historical basis | Not remaining avoidable cost

## 07 Cost Build Up
Candidate Methodology - Detailed Cost Build-Up
WARNING: Total is incomplete while any TBC rate or quantity remains. Rates are AUD ex GST.
Cost code | Cost group | Item | Qty | Unit | Rate | Duration / multiplier | Extended cost | Rate status | Source / note
ENG-SURV | Engineering | Bathymetric and seabed survey | 1 | LS |  | 1 |  | TBC | Obtain supplier quote
ENG-TW | Engineering | Temporary works design and independent check | 1 | LS |  | 1 |  | TBC | Platform/hang-off/traversing decks
ENG-CONT | Engineering | Containment and environmental design | 1 | LS |  | 1 |  | TBC | Pile and headstock configurations
ENG-MAR | Engineering | Marine operations plan, SIMOPS, rescue and seasonal plans | 1 | LS |  | 1 |  | TBC | Stage 1 / execution engineering
MOB-JUB | Mobilisation | JUB mobilisation to Lucinda | 1 | LS |  | 1 |  | TBC | Candidate unit required
MOB-PLAT | Mobilisation | GGC platform transport, assembly and modification | 1 | campaign |  | 1 |  | TBC | Use written GGC quote
MOB-CONT | Mobilisation | Containment/traversing deck fabrication and assembly | 1 | campaign |  | 1 |  | TBC | Supplier quote
MOB-TEST | Mobilisation | Proof load and proving campaign | 1 | campaign |  | 1 |  | TBC | Include engineering attendance
TIME-JUB | Time-related | Jack-up barge hire | 1 | day |  | 0 |  | TBC | Duration from dated programme
TIME-WB | Time-related | Primary workboat / multicat hire | 1 | day |  | 0 |  | TBC | Campaign duration
TIME-RB | Time-related | Dedicated rescue craft | 1 | day |  | 0 |  | TBC | Whenever personnel over water
TIME-PLAT | Time-related | Floating platform/access set hire | 1 | set-day |  | 0 |  | TBC | Fleet output from model
TIME-CONT | Time-related | Containment set hire/ownership | 1 | set-day |  | 0 |  | TBC | Fleet output from model
TIME-UTIL | Time-related | Compressors, generators, breathing air, extraction and vacuum plant | 1 | day |  | 0 |  | TBC | JUB service spread
TIME-BASE | Time-related | Shore base, stores, waste and vehicles | 1 | day |  | 0 |  | TBC | Local logistics
LAB-MGMT | Labour | Project manager / construction manager | 1 | person-day |  | 0 |  | TBC | Resource-loaded programme
LAB-MAR | Labour | Marine superintendent / barge master / deck crew | 1 | person-day |  | 0 |  | TBC | Marine spread
LAB-HSE | Labour | HSE and environmental supervision | 1 | person-day |  | 0 |  | TBC | Shift coverage
LAB-QA | Labour | QA, coating inspector and records | 1 | person-day |  | 0 |  | TBC | Shift coverage
LAB-INSP | Labour | Inspection / UT / NDT crew | 1 | crew-day |  | 0 |  | TBC | Ahead and release fronts
LAB-WELD | Labour | Two-person welding crew | 1 | crew-day |  | 0 |  | TBC | Crew count from scenario
LAB-COAT | Labour | Blasting/coating crew | 1 | crew-day |  | 0 |  | TBC | Containment fronts
LAB-JKT | Labour | Jacket installation crew | 1 | crew-day |  | 0 |  | TBC | Tide/marine method
LAB-RIG | Labour | Rigging/platform relocation crew | 1 | crew-day |  | 0 |  | TBC | Advance rigging + move
CONS-STEEL | Per bent | Repair steel and fabrication | 53 | lm |  | 227 |  | TBC | 52.6 lm/payment equivalent sensitivity
CONS-WELD | Per bent | Welding consumables and NDT | 53 | lm |  | 227 |  | TBC | Accepted repair quantity
CONS-BLAST | Per bent | Abrasive and recovery/disposal | 49 | m2 |  | 227 |  | TBC | Typical whole-bent area; family model required
CONS-COAT | Per bent | Dulux Duremax GFX coating system | 49 | m2 |  | 227 |  | TBC | Two 500 micron coats + stripe
CONS-JKT | Per pile | Petrolatum jacket system | 2 | pile |  | 227 |  | TBC | Typical bent only; family mix required
OPS-ACCOM | Operations | Accommodation and meals | 1 | person-day |  | 0 |  | TBC | Peak crew x campaign days
OPS-FUEL | Operations | Fuel and lubricants | 1 | day |  | 0 |  | TBC | JUB/boats/generators
OPS-WASTE | Operations | Hazardous and general waste treatment | 1 | campaign |  | 1 |  | TBC | Mass balance required
OPS-SHIP | Operations | Ship-call make-safe and restart allowance | 1 | event |  | 0 |  | TBC | 10-14 calls/year planning range
OPS-SEASON | Operations | Wet-season demob/remob and cyclone recovery | 1 | season |  | 2 |  | TBC | Full Dec-Mar demob
CONT | Contingency | Risk allowance | 1 | % |  | 0 |  | TBC | Apply after estimate basis is complete
Subtotal of completed numeric lines
Estimate completeness
Issue status

## 08 Productivity
Proposed Productivity Model - Access-Set Occupancy
Input | Value | Unit | Basis / note
Whole-scope stress quantity | 227 | bents | Unverified stress case pending bent register
Nominal production seasons | 2 | seasons | 2027 and 2028
Nominal weeks per season | 30 | weeks | Before explicit calendar losses
Required net stress rate |  | bents/week | 227 / 60
Working days per week | 6 | days/week | Planning input
Shifts per day | 1 | shift/day | Night production not assumed
Residual stochastic availability | 0.85 | factor | Weather/breakdown only; known outages explicit
Weld quantity per typical bent | 53 | lm | Payment-equivalent sensitivity, not design quantity
Weld crews per access set | 2 | crews | Base sensitivity
Accepted weld output per crew shift | 6 | lm/crew-shift | Unverified central sensitivity
Repair approval hold | 3 | days | Bent-level approval basis requiring confirmation
Relocation hours per bent | 11 | h | Advance rigging + move package
Hours per shift | 10 | h | Planning input
Headstock containment/work | 0 | shifts | NOT MODELLED; enter only with evidence
Below-LAT jacket work | 0 | shifts | NOT MODELLED
Containment cleanout/QA/rework | 0 | shifts | NOT MODELLED
Coating elapsed hold occupancy | 0 | days | NOT MODELLED; dated work-lot required
Model activity | Base active/hold shifts | Formula / basis | Status
Wash, inspect and UT | 1 | Project/programme basis | Included
Diagnostic blast: two upper pile bands | 1 | ~27-29 m2; conservative incl containment moves/QA | Included
Mark-up and bent repair package | 0.5 | Engineering assumption | Included
Repair approval hold |  | One bent-level hold; confirm | Included assumption
Welding and NDT |  | Weld qty / crews / accepted rate | Largest modelled item
Post-weld preparation | 0.5 | Engineering assumption | Included
Coating active work | 1.5 | Does not include elapsed recoat holds | Included active only
Jacket active work above LAT | 1 | Timed trial required | Included assumption
Headstock containment/work |  | User evidence input | NOT MODELLED if zero
Below-LAT jacket work |  | User evidence input | NOT MODELLED if zero
Cleanout/QA/rework |  | User evidence input | NOT MODELLED if zero
Coating elapsed hold occupancy |  | User evidence input | NOT MODELLED if zero
Relocation |  | 11 h / shift hours | Included
Total access-set occupancy cycle |  | shifts/days at one shift/day; still concept-stage
Rate per access set |  | bents/week/set
Sets required for stress rate |  | mathematical sensitivity, not recommended fleet
Access sets | Calculated bents/week | Weeks for 227 bents | Nominal seasons | Gap to 3.783/week
1
2
3
4
5
6
7
8
9
10
11
12

## 09 Fleet Scenarios
Fleet and Welding Capacity Sensitivities
Scenario | Weld crews/set | Accepted lm/crew-shift | Routine approval hold (d) | Other fixed shifts | Relocation shifts | Cycle shifts | Rate/set/week | Sets required | Indicative weld crews | Status / interpretation
S1 Base incomplete | 2 | 6 | 3 | [6 empty] | Diagnostic sensitivity only; open activities remain.
S2 Improved welding | 4 | 8 | 3 | [6 empty] | Diagnostic sensitivity only; open activities remain.
S3 Repair library / reduced hold | 4 | 8 | 0 | [6 empty] | Diagnostic sensitivity only; open activities remain.
S4 Strong weld + reduced hold | 6 | 10 | 0 | [6 empty] | Upper-bound sensitivity; not executable without proving.

## 10 Programme
Indicative Stage 1 to Execution Programme and Calendar Gates
WBS | Activity | Responsible party | Start basis | Duration weeks | Predecessor | Calendar treatment | Output / acceptance
A1 | STL confirm priority and remaining bent register | STL | Immediate | 1 | None | Working days | As-at-date register by bent/family/status
A2 | Bathymetric/seabed and metocean data confirmation | STL / surveyor | Immediate | 4 | None | Marine survey window | Data accepted for JUB/platform design
A3 | GGC platform/containment technical and commercial offer | GGC | Immediate | 2 | None | Calendar | Dimensions, mass, capacity, winch, availability, rates
A4 | JUB/workboat market sounding and quotes | Endura / suppliers | Immediate | 2 | None | Calendar | Candidate spread, availability, rate and limitations
A5 | Concept option screening and STL workshop | Endura / STL | After A1-A4 initial | 1 | A1,A3,A4 | Working days | Selected direction and actions
B1 | Temporary works concept and load-path design | Execution contractor/RPEQ | After supplier selection | 6 | A2,A3,A5 | Working days | Checked concept drawings and load schedule
B2 | Containment/headstock/below-LAT method development | Supplier / engineer | After supplier selection | 6 | A3,A5 | Working days | Accepted method and cycle basis
B3 | Marine operations, SIMOPS, environmental and approvals plan | Marine/HSE team | After A2,A4 | 8 | A2,A4,A5 | Working days | Approval-ready plans
B4 | Detailed cost, dated programme and procurement strategy | Endura | After B1-B3 | 4 | B1,B2,B3 | Working days | Board-ready comparison
C1 | Fabricate/modify access sets and containment | Supplier | After approval | 10 | B1,B2,B4 | Calendar/long lead | Factory acceptance and load test
C2 | Mobilise marine spread and establish shore base | Contractor | Dry-season start | 3 | C1,B3 | Marine weather | Ready for proving
C3 | Two-set proving campaign on representative bent families | Contractor / Endura / STL | After C2 | 4 | C2 | Dated calendar | Timed cycles, acceptance, safe limits
C4 | Update fleet/resource/cost model and production decision | Endura / STL | After proving | 2 | C3 | Working days | Approved production configuration
D1 | Production ramp-up | Contractor | After C4 | 4 | C4 | Explicit ramp-up | Stable QA-closed output
D2 | 2027 production season | Contractor | Mar-Nov 2027 | 30 | D1 | Explicit outages/ship calls | QA-closed bents
D3 | Wet-season demob and preservation | Contractor | Dec 2027-Feb 2028 | 12 | D2 | No production | Fleet secured/preserved
D4 | 2028 remobilisation and production | Contractor | Mar-Nov 2028 | 30 | D3 | Explicit outages/ship calls | Priority scope complete by end 2028

## 11 Comparison
Current Method versus Candidate Marine Access System
Criterion | Current scaffold methodology | Candidate marine access methodology | Evidence maturity | Decision consequence
Access establishment | Full scaffold and encapsulation built/stripped at each bent, typically 3-5 days combined access handling | Reusable platforms lowered, towed, lifted and recommissioned; current working allowance 11 h per move | Current verified; proposed unverified trial basis | Strong potential schedule improvement if supplier configuration and weather limits are proven
Current demonstrated output | 0.36 safe-access bent-equivalents/week; completed-bent rate not verifiable | Output is scenario-based QA-closed bents/week; no demonstrated project rate yet | Current claim evidence vs proposed model | Do not present a direct uplift ratio
Workface concurrency | Four scaffold sets did not give four continuously usable fronts; up to nine bents WIP in programme | Multiple access sets/pairs can be scaled; final fleet is model output | Concept only | Two sets are proving pair, not automatically production fleet
Approval hold | Approximately 3 days with scaffold standing | One bent-level hold proposed after exposing both piles/headstock; repair library sensitivity | Requires Jed/reviewing engineer confirmation | Can materially alter fleet requirement
Welding | 473 lm claimed; ~52.6 lm per inspection-equivalent; 10 mm dominates | Largest modelled activity; accepted lm/crew-shift and safe zones must be trialled | Current quantity verified; proposed rate assumption | May drive crew/fleet configuration
Containment | Whole bent scaffold wrap | Reusable half-shell pile containment; headstock enclosure unresolved | Supplier gate | Major constructability and environmental gate
Tide exposure | Lower access and jackets tide/weather limited | Platform follows work height; below-LAT jacket remains unresolved | Partial | Reduces but does not eliminate tidal dependence
Roadway logistics | Single lane used for scaffold/materials and light plant | Crew/light duties by road; heavy materials, utilities and waste via JUB/water | Concept | Reduces congestion subject to marine logistics capacity
Ship/cyclone response | Make-safe and weather disruption evidenced | Two-day ship make-safe, full wet-season demob and cyclone recovery to be timed | Open gate | Can consume calendar and fleet capacity
Cost basis | Current contract access basis known but remaining avoidable cost not reconciled | Detailed bottom-up model prepared; total incomplete until rates/duration/fleet are closed | Partial | No unsupported saving claim

## 12 Risks & RFIs
Risk, Verification Gate and RFI Register
ID | Category | Risk / open item | Consequence | Required evidence / action | Owner | Due | Status | Affects cost | Affects programme | Affects safety
R01 | Scope | Priority boundary and current remaining bent/family status not confirmed | Required rate, fleet, cost and method assignment remain uncertain | STL issue controlled bent register | STL |  | Open | Y | Y | N
R02 | Platform | Selected GGC platform mass, freeboard, deck load and lifting points not confirmed | Hoist and temporary-works feasibility unverified | Written GGC/Hansen technical schedule | GGC |  | Open | Y | Y | Y
R03 | Suspension | Winch location, travelling clamp range and locking not defined | Platform may not follow pile rake or survive fault cases | Supplier concept + RPEQ design | GGC/RPEQ |  | Open | Y | Y | Y
R04 | Traversing decks | Load path between independently suspended platforms undefined | 360-degree access may be unsafe/unworkable | TW design and trial | RPEQ/GGC |  | Open | Y | Y | Y
R05 | Containment | Half-shell alignment and headstock enclosure not defined | Blast/coating productivity and environmental control unproven | Supplier design, airflow/noise/waste tests | Supplier |  | Open | Y | Y | Y
R06 | Jackets | Below-LAT installation and lower termination unresolved | Bent closeout cycle incomplete | Manufacturer/marine method and trial | Supplier |  | Open | Y | Y | Y
R07 | Approval | One bent-level three-day approval basis not confirmed | Additional holds can increase cycle/fleet materially | Jed and reviewing engineer decision | Endura/STL |  | Open | N | Y | N
R08 | Welding | Accepted lm/crew-shift and simultaneous safe weld zones unproven | Largest modelled activity may be understated | Timed trial incl fit-up/NDT/rework | Contractor |  | Open | Y | Y | Y
R09 | Coating | Active work separated from elapsed recoat holds; dated work-lot logic incomplete | 14.02-day cycle is not demonstrated elapsed occupancy | Manufacturer advice and proving cycle | Coating supplier |  | Open | Y | Y | Y
R10 | Marine spread | Bathymetry, leg penetration, JUB reach and service capacity unresolved | JUB may not cover assumed workfronts or inshore area | Survey + candidate JUB study | STL/Marine supplier |  | Open | Y | Y | Y
R11 | Calendar | Ship calls, outages, weather and wet-season blocks not fully dated | Required production window can be overstated | Dated calendar model | STL/Planner |  | Open | Y | Y | Y
R12 | Cyclone | Full fleet recovery within warning time not demonstrated | Asset/environmental exposure and loss of season | Timed recovery plan/drill | Marine contractor |  | Open | Y | Y | Y
R13 | Environmental | GBRMPA/port/ecology/waste permissions not confirmed | Approval delay or method restriction | Regulatory pathway and permit matrix | Endura/STL |  | Open | Y | Y | Y
R14 | Insurance | Marine plant, P&I, professional and environmental cover not confirmed | Uninsured exposure/procurement delay | Broker review by vessel/operation class | Contractor/STL |  | Open | Y | Y | Y
R15 | Commercial | GGC/JUB/labour rates and current remaining contract cost not reconciled | No board-defensible cost comparison | Written quotes and certified cost-to-complete | Endura/STL |  | Open | Y | Y | N

## 13 Dashboard
Executive Dashboard - Current Evidence and Candidate Sensitivities
Required stress rate | Current safe-access claim rate | Base model cycle | Decision statement
Two complete access sets should be treated as a proving/leapfrog pair, not the demonstrated production fleet. Final fleet and cost require supplier data, a timed trial and the dated calendar.
QA-closed bents/week | stage eq/week | shifts/set
Base rate per set | Base sets required | Estimate completeness
bents/week/set | diagnostic sets | % numeric lines