## README
ED-018-2026-06 ACCESS OPTIONS MODEL REV B
Companion to report ED-018-2026-02 Rev B, 26 August 2026. Commercial in confidence.
What changed at Rev B
Scenarios sheet added: the marine base with and without, at current and serviced trade productivity, with live formulas.
BaseMenu sheet added: concepts C0 to C6, each with its own cycle and availability assumption.
Levers sheet rebuilt per option so every package reconciles from the lines above it.
Inputs sheet extended with the written marine rate references of 24 August 2026.
Sensitivity relabelled: the reported case is the marine review upper band; the old model base tag removed.
Programme sheet extended with Option 1, zone phased and compressed day finish dates.
Reading order: Inputs, Options, Scenarios, BaseMenu, Levers, Sensitivity, Programme, NoBase, RateCard.
Every figure quoted in the report traces to one of these sheets.

## Options
Option 1 base case against Option 2 optimised, night shift on trades
Both options use the same trade content, the same crews and the same rates. Only the access arrangement differs.
| OPTION 1 Base case Day shift only, as Draft A | OPTION 2 Optimised Trades day & night, platforms move in daylight only | Note
THE CYCLE
Trade shifts worked per calendar day | 1 |  | Option 2 adds a night shift on the trades only, derated for night productivity
Effective access days per bent |  |  | Moves are daylight only in both options. Platform is floating during a move, so it carries the floating availability
Effective trade days per bent |  |  | Once lifted and transferred onto positive ties the platform is a fixed suspended platform, so trade work carries the fixed availability
Approval hold days |  |  | Removed in both options if the repair library is agreed under contract Appendix J
EFFECTIVE CYCLE, days per bent
THE FLEET
Bents per week, one front
Bents per week required |  |  | 227 bents across the two available seasons
WORK FRONTS REQUIRED |  |  | One front = two floating stage halves working one bent
Stage halves in the water |  |  | Supplier holds five platforms today. The balance is the fleet build, still POA
Chain blocks required |  |  | Four Kito 2 t per front
Clamp sets rigged (working plus one bent ahead)
Campaign weeks
HEADCOUNT
Trade heads on shift (contractor's cost, not ours) |  |  | Five trades per face. Option 2 runs two crews per front. Total trade person-shifts is identical at 227 x 7 x 5 = 7,945
Access crew, day shift |  |  | Riggers, scaffolders, coxswains. A fleet crew, not a per front crew
Access crew, night shift | 0 |  | Option 2 only. No moves, no lifting, no man riding at night. Rescue capability and permit control still required
Total on site
ACCESS COST, our scope only
Access kit and support crane |  |  | Winch sets, pontoons, module, davit per front, plus one support crane for the fleet at the card low band
Marine base, operating |  |  | Largest single line. Manned jack up is the base for service autonomy: air, power, welding, welfare on the water. Spud flat top remains a priced lever with its service continuity risk stated
Access labour |  |  | Access crew only. Trade labour stays inside the contractor lump sums and is excluded from this estimate
Fixed access lines |  |  | Identical in both options
Subtotal
Contingency |  |  | AACE Class 5
ACCESS TOTAL
Access cost per bent
Saving of Option 2 against Option 1
WHAT ELSE CHANGES
Marine risk exposure | Moves, lifting and man riding in daylight only | Unchanged. No moves, no lifting, no man riding at night. Night work is trade work on a platform already lifted and tied off, accessed from the jetty deck | Option 2 does not add marine risk, it adds hours on a static platform
Rescue over water | Day only | Required at night as well. The one marine duty that does not go away | Cost carried in the night standby crew above
Recoat window | Blast and first coat can fall either side of a night, risking flash rust and rework | Blast runs into first coat across the day and night boundary, inside the window | The incumbent record already shows defects found after blast, reblast and touch up
Fabrication lead time | More halves to build before a March 2027 mobilisation | Fewer halves. This is the largest programme benefit, not the cost saving | Fleet build is still POA in both options
Accommodation, Ingham | Fewer beds | More beds, and two shift patterns to roster | Trade contractor's cost, but STL will ask
Light spill, marine park | Not applicable | GBRMPA question. The encapsulated habitat contains most of it | Raise in the approvals pathway
Before Option 2 goes to STL, verify: (1) that night work is a choice and not a prohibition under the contract, MSQ, the port authority or GBRMPA, since Draft A states it as a site constraint; (2) the night rescue and medevac arrangement; (3) light spill against the marine park conditions; (4) that the coating supplier supports night application.
PATTERN B, compressed day (added Rev B): both trade shifts inside 0600 to 2200; cycle about 7.4 days, 0.82 bents per front week, six fronts at reported availabilities, access total about $13.95M; the 2200 to 0700 band is never entered and the 1800 to 2200 noise limit equals the daytime limit at background plus 10 dB(A). Roster subject to trade contractor confirmation.

## Inputs
ED-018-2026-06 Access Options Model, Rev A
Lucinda jetty remediation. Two access options compared on one basis. Access scope only: trade works are held at the contractor's own durations, crews and rates and are not re-priced.
Blue cells are inputs you may change. Yellow cells are unconfirmed with the owner named. Everything else is formula.
Input | Value | Unit | Source and confidence
Priority bents | 227 | ea | Contract Appendix D priority scope. Planning basis pending the STL bent register
Available weeks | 50.4 | wk | Two 26 week seasons less 1.6 ship call weeks
Working days per week | 6 | d | No Sundays, no seventh day
Access (move) shifts per bent | 2 | sh | Supplier stated: move on 1, move off 1
Trade shifts per bent | 7 | sh | Contractor programme, held identical in both options
Approval hold | 3 | d | Contractor programme column
Repair library agreed (1 yes, 0 no) | 1 | flag | STL decision under contract Appendix J; the executed contract itself carried a night work provision
Availability: platform floating, during moves | 80% |  | Marine review upper band. The manned jack up base with a support crane holds move windows; the 2026 trial measures the achieved figure before the fleet order
Availability: platform fixed on positive ties, trade work | 90% |  | Fixed suspended platform, enclosed habitat, night continuity. Upper band of the marine review; trial measured
Night crew productivity vs day | 100% |  | Night trades on a tied, lit, enclosed platform with crib and services on the base lose no productivity; declared, trial measured
Access crew per front | 1.3333 | heads | 12 heads at 9 fronts: riggers, scaffolders, coxswains. Day shift only
Night standby crew: rescue coxswain and crew, permit officer | 2 | heads | Option 2 only. Required, not optional: crews work over water at night
Access crew head day cost, day shift | 1471.43 | $/d | Contract schedule of rates 4.1.2 scaffolder at 110 for 2027 for five access crew, with coxswain and deckhand from the supplier card where the contract carries no marine role. Ten hour shift plus 350 allowances
Marine base, operating | 10000 | $/d | ABH SeaLift 6 via T Glenister 20 Aug. CONFLICTS with $32,000/month on file
Access kit per front | 5400 | $/front-wk | Basis: winch set 2,500 + pontoons 1,400 + module 1,500
Contingency | 25% |  | AACE Class 5 screening
Support crane, platform moves and recovery | 2600 | $/wk | Card low band, Franna class. One crane serves the fleet; day hire at mobilisation sits in the haulage line
Night standby head day cost | 1877.5 |  | Coxswain and deckhand blended, plus the 30 percent nightshift uplift from the supplier card note 6.5, ten hour shift plus 350 allowances
Nightshift uplift applied | 30% |  | GGC rate card pricing note 6.5
Clamp and suspension certification, lift plans, man-riding certs | 55500 |  | Supplier scope, two engineers
Approvals, inductions, VOCs, first-fit PPE, access crew | 27750 |  | Card 6.1
Blastclad containment skin, $350 x 227 bents | 79450 |  | Containment is part of the platform
Assemble and proof load each front | 66600 |  | 3 riggers and leading hand, 1 shift per front
Marine mobilisation, tow in, establish | 148500 |  | Timing dependent
Kit haulage, 8 semis | 121500 |  | Crawler POA
Rescue proof and cyclone recovery drill | 55500 |  | Gate before the fleet grows
Trial bent proven to the Superintendent | 155400 |  | Calibrates the true cycle
Marine standby through the wet season | 910000 |  | 26 wk at half rate. TBC line by line
Kit standby through the wet season | 475800 |  | Electrical and vehicles off site
Workboat and vehicles | 216209 |  | Does not reconcile to Basis rates, see comment schedule
Demobilise marine and kit | 150000 |  | Timing dependent
Records, MDR, DLP allowance | 18500 |  | Contract 8.1.0
Subtotal, fixed access lines
Not priced in either option: fleet build or hire (Activity 2.1, POA, five platforms exist), marine hull and P&I insurances, GBRMPA and MSQ permits, port charges, accommodation, escalation from August 2026 money.
CURRENT METHOD ACCESS, contract rates
Scaffold hire, typical pilebent | 88.2 | $/day | Contract schedule of rates 4.2.10, 2027 column
Scaffolder | 110 | $/hr | Contract schedule of rates 4.1.2, 2027 column
Supervisor | 130 | $/hr | Contract schedule of rates 4.1.5, 2027 column
Scaffold team | 5 | heads | Tender Schedule E1: one supervisor and four scaffolders
Erect and dismantle per bent | 5 | days | Contractor programme, five of the fifteen day cycle
Scaffold occupancy per bent | 15 | days | Contractor programme cycle
Access labour per bent, current method |  | $ | One supervisor and four scaffolders, ten hour shifts, over the erect and dismantle days
Scaffold hire per bent, current method |  | $ | Hire rate over the occupancy days
Current method access per bent |  | $
Current method access, 227 bents |  | $ | Cross check against the stated access allowance of about 9.3M
CURRENT ACCESS ALLOWANCE, DERIVED FROM THE PRICED SCHEDULE
2.1.1 typical pilebent, 212 bents | 6344314.51 |  | Priced schedule, provision of safe access
2.2.1 anchor bent type A | 241542.45 |  | Priced schedule, provision of safe access
2.3.1 anchor bent type B | 192857.5 |  | Priced schedule, provision of safe access
2.4.1 passing bay | 270536.95 |  | Priced schedule, provision of safe access
2.5.1 special bent | 182613.13 |  | Priced schedule, provision of safe access
2.6.1 expansion joint | 113094.5 |  | Priced schedule, provision of safe access
2.7.1 special | 50601.44 |  | Priced schedule, provision of safe access
2.8.1 inclusive access | 68131.29 |  | Priced schedule, provision of safe access
2.9.1 QSL install allowance | 1131509.26 |  | Priced schedule, provision of safe access
2.12.1A nominated pile 1 | 181969.9 |  | Priced schedule, provision of safe access
2.12.1B nominated pile 2 | 39684.93 |  | Priced schedule, provision of safe access
2.12.1C both piles typical | 167594.41 |  | Priced schedule, provision of safe access
2.14.1 underpass | 108022.46 |  | Priced schedule, provision of safe access
2.15.1 underpass | 150305.81 |  | Priced schedule, provision of safe access
Total access allowance in the priced schedule |  |  | Confirms the figure carried in the report as about 9.3M
Typical pilebent safe access, 2026/27 | 28965.58 |  | Priced schedule 2.1.1, 2026/27 column
Typical pilebent safe access, 2027/28 | 30413.86 |  | Priced schedule 2.1.1, 2027/28 column
Cross check from variation rates | 29823 |  | Contract 4.1.2, 4.1.5 and 4.2.10 build up; sits between the two priced years
WRITTEN MARINE RATE REFERENCES, added at Rev B
Jack up barge, active hire | 10000 | $/d | Carried rate; ABH SeaLift 6 via T Glenister 20 Aug; marine contractor concept submission 24 Aug 2026 carries the same figure in writing (budget status); ABH written reconciliation letter issued, remains the pre workshop action
Jack up barge, wet season standby | 30000 | $/wk | Marine contractor concept submission 24 Aug 2026, written budget rate; model retains $35,000 per week (half day rate) as the conservative carry
Barge mobilisation and demobilisation | 120000 | lump sum | Marine contractor concept submission 24 Aug 2026, midpoint of $80,000 to $140,000; used in lever L2
Marine spread cross check | 4890000 | $ | Same submission prices the equivalent spread at $4.89M on a 60 week programme: 420 active days at $10,000 plus 19 weeks standby at $30,000 plus one mobilisation

## Scenarios
THE MARINE BASE, WITH AND WITHOUT: COST AND PRODUCTIVITY (Option 1, day shift)
Live formulas. Trade shifts per bent is the productivity dial: 7.0 is the current contractor content, 6.0 is the serviced case, about one shift per bent recovered where work is crew paced. Cure, tide and approval waits gain nothing.
Scenario | Trade shifts/bent | Fixed avail | Fronts | Cycle d | Rate /front/wk | Campaign wk | Access $M | Modelled note
Without base: current productivity, wharf serviced | 7 | 0.82 | 9 |  |  |  |  | Finish late Sep 2028; services queue on the roadway
With base: tendered content held (conservative, reported) | 7 | 0.9 | 8 |  |  |  |  | Finish 11 Oct 2028; the Rev A basis
With base: serviced productivity, central case, fleet held | 6.5 | 0.9 | 8 |  |  |  |  | Finish 17 Sep 2028; optimistic bound 6.0 shifts gives $14.64M, 5 Sep
With base: serviced at the optimistic bound, fleet trimmed | 6 | 0.9 | 7 |  |  |  |  | Finish 18 Oct 2028; one less front to fabricate
True net cost of the base once productivity is counted: serviced fleet held minus without base
Basis of the serviced case: about 12 minutes each way on the roadway with passing bay waits, two crib runs and shift end, about 58 minutes per 10 hour shift; applied only to the crew paced share of the seven trade shifts (weld, blast, coat, wrap), worth about one shift per bent. Band 6.0 to 6.5 shifts; 6.0 carried.
OPTION 2 REFERENCES (two trade shifts per calendar day; same formula structure)
With base, serviced 6.0 trade shifts |  |  | 5 |  |  |  | 13.25 | Finish 10 Sep 2028
Compressed day pattern, serviced 6.0 |  |  | 6 |  |  |  | 12.92 | Finish late Aug 2028

## Sensitivity
Does the answer move? Fronts required under each availability scenario
This is the case for Option 2. Option 1 swings by five fronts across the range; Option 2 holds.
Scenario | Floating availability (moves) | Fixed availability (trade) | Opt 1 cycle, days | Opt 1 FRONTS | Opt 2 cycle, days | Opt 2 FRONTS
Marine review, pessimistic | 60% | 80%
Marine review, mid | 70% | 85%
Marine review, optimistic | 80% | 90%
Draft A blanket 0.85 | 85% | 85%
Other stresses on Option 2 (mid availability unless stated)
Stress | Opt 2 fronts
Night crew only 80 percent as productive
Marine moves take 3 days, not 2
Repair library NOT agreed
Scope is 257 bents, not 227
Pessimistic availability AND no library
A recommendation that holds still when the metocean lands is worth more to a risk averse board than a lower number that moves.
Compressed day pattern, trades 0600 to 2200 (Option 2 pattern B) | n/a | 6 | Both trade shifts inside 0600 to 2200; 7 at mid availability; roster subject to trade contractor confirmation

## Programme
SEASON PROGRAMME, Option 2 reported case
Season level calculation from the reported fronts, cycle and calendar. A dated bent by bent programme with approvals, fabrication, outages and ship calls is a hold point deliverable before the fleet order.
Bents in the priority planning basis |  | ea | Pending the STL priority and closeout register
Fronts, Option 2 reported case |  | ea | From the Options sheet
Bents per week, one front |  |  | From the Options sheet
Fleet rate |  | bents/wk | Fronts times front rate
Season 1 start | 2027-05-03 |  | After mobilisation, assembly and proof loading
Season 1 available weeks | 26 | wk | 3 May to 31 October 2027
Ramp weeks at 60 percent | 2 | wk | First fronts through the learning curve
Season 1 bents |  | ea | Computed
Carried into season 2 |  | ea | Computed
Season 2 start | 2028-05-01 |  | After the wet season lay up
Weeks required in season 2 |  | wk | Computed
Modelled finish |  |  | Computed
Days before the 1 November closure |  | d | Operational margin
Days before the administrative end 2028 date |  | d | Contract margin
ADDED AT REV B
Option 1, 8 fronts at reported availabilities: season one about 118 bents, season two 23.4 weeks, modelled finish 11 Oct 2028, 21 days before closure | computed
C2 zone phased, fleet held: season two at 0.82 fixed availability runs 25.1 weeks, modelled finish about 23 Oct 2028, 9 days before closure | computed
C2+ one added season two front: 22.3 weeks, modelled finish about 4 Oct 2028, 28 days before closure | computed
Compressed day pattern (Option 2 pattern B), 6 fronts: campaign 46.4 weeks, finish inside season two with about 3 weeks float | computed

## RateCard
ACCESS RATES TRACED TO THE SUPPLIER RATE CARD
GGC Rate Card dated 20 August 2026, rates exclude GST. Every access rate used in this model is listed against its card line.
KIT BUILD UP, one front week
4 x Kito 2 t electric chain block | 200 | per week each | 800 | Card 4.92
Control panel and wireless pendant | 500 | per week | 500 | Card 4.93
4 x 9 m modular pontoon | 100 | per day each | 2400 | Card 4.7, six day week
240 v winch with davit arm, SWL 500 kg | 500 | per week | 500 | Card 4.97
20 kVA genset | 1200 | per week | 1200 | Card 4.98
Kit total per front week |  |  | 5400 | Reconciles to Inputs B20
OTHER CARD RATES USED
20 t Franna support crane | 2600 | per week |  | Card 5.2, minimum hire six months; campaign is 48 weeks
Scaffolder and rigger | 140 | per hour |  | Card 2.4
Coxswain | 125 | per hour |  | Card 2.3
Deckhand | 110 | per hour |  | Card 2.2
Blended access labour used in this model | 150 | per hour |  | Above the card trades listed; conservative, covers leading hand and fitter content
Living away from home allowance | 300 | per day |  | Card 3.6
Remote area allowance | 50 | per day |  | Card 3.9
Allowances used in this model | 350 | per day |  | Card 3.6 plus 3.9
Night shift uplift | 30% | on labour |  | Card pricing note 6.5
CARD CONDITIONS CARRIED
Minimum charge out | 8 hours |  |  | Card 6.3; model uses 10 hour shifts
Annual rate increase | excluded |  |  | Card 6.2; escalation is a stated exclusion
Consumables at cost plus | noted |  |  | Card 6.9; trade consumables sit outside this access scope
ACCESS LABOUR BUILD UP, from the card
5 x scaffolder or rigger | 140 | per hour |  | Card 2.4
1 x coxswain | 125 | per hour |  | Card 2.3
1 x deckhand | 110 | per hour |  | Card 2.2
Leading hand allowance | 10 | per hour |  | Card 3.1, one of seven
Day crew blended | 135 | per hour |  | Weighted over the seven heads
Day head day cost | 1700 | per 10 h shift |  | Blended rate plus 350 allowances
Night standby blended | 117.5 | per hour |  | Coxswain and deckhand only
Night head day cost | 1877.5 | per 10 h shift |  | Blended rate plus 30 percent uplift, plus 350 allowances
Trade labour | excluded |  |  | Remains inside the contractor lump sums; unchanged by this study
CONTRACT SCHEDULE OF RATES USED, 2027 COLUMN
Scaffolder | 110 | per hour |  | Contract 4.1.2
Labourer | 110 | per hour |  | Contract 4.1.3
Supervisor | 130 | per hour |  | Contract 4.1.5
Boilermaker | 150 | per hour |  | Contract 4.1.1
Scaffold hire, typical pilebent | 88.2 | per day |  | Contract 4.2.10
Compressor | 310 | per day |  | Contract 4.2.4
Generator | 485 | per day |  | Contract 4.2.2
Airprep | 80 | per day |  | Contract 4.2.6
Coxswain | 125 | per hour |  | Supplier card 2.3, no contract equivalent
Deckhand | 110 | per hour |  | Supplier card 2.2, no contract equivalent

## NoBase
OPTION 1 WITHOUT A FLOATING MARINE BASE
Requested by STL 21 August 2026. Services taken from the wharf using the existing layup areas and wharf head facilities, as described by STL. Indicative; the operability derate and the deck services build are engineering judgement and are to be tested at the proving trial.
Floating availability, moves | 0.8 |  | Unchanged; workboat and crane still support moves
Fixed availability, trade work | 0.82 |  | Derated from 0.90: crews transit to wharf head or layup areas for amenities and stores
Effective cycle |  | days | Same trade content, no night shift
Bents per week, one front |  |  | Six day week
Fronts required |  | ea | Rises from eight
Campaign weeks |  | wk
Access kit and support crane |  | $ | Card rates, unchanged
Deck based services |  | $ | Generator 485, compressor 310, airprep 80 per day, one set per two fronts, contract items 4.2.2, 4.2.4 and 4.2.6
Access crew labour |  | $ | Contract rates 4.1.2 and 4.1.5
Fixed lines, marine base items removed | 1480709 | $ | Marine standby and part of marine mobilisation removed; workboat, certification, trial and kit standby retained
Subtotal |  | $
Contingency 25 percent |  | $
TOTAL, no floating base |  | $
Option 1 with the jack up |  | $ | For comparison
Difference |  | $ | Saving from removing the base, net of the deck services it needs
Fronts, with base against without |  | ea | Compare with the fronts figure above

## Levers
COST LEVERS, rebuilt per option so every package reconciles from the lines above it
All values AUD millions. Pre contingency unless stated. Contingency 25 percent applied at package level, 15 percent at the award step.
Lever | Option 1 (day shift) | Option 2 (day and night) | Basis / what must be true
Reported build, pre contingency | 12.83 | 11.37 | Options sheet subtotals
L1 Marine base: moored spud flat top at $3,000 per day in place of the manned jack up at $10,000 per day; wet standby at half rate each | 3.02 | 3 | Written spud quotation carrying the same services; boarding in weather risk stated
L2 Wet season: barge off hire and shore lay up in place of half rate standby, net of one written $120,000 remobilisation lump sum; fleet lay up care retained within existing lines | 0.79 | 0.79 | Off hire and remobilisation terms agreed; season two availability secured
L3 Night rescue reclassification: dedicated night standby crew released (Option 2 only) | 0 | 1.09 | Safety case accepts the lifted, tied and enclosed platform as a fixed workplace; regulator concurrence
PACKAGES, with 25 percent contingency unless stated
Reported base | 16.04 | 14.22 | As issued
Credible: L1 plus L2 | 11.28 | 9.47 | (pre cont minus L1 minus L2) x 1.25
Stretch: plus L3 (Option 2 only) | 11.28 | 8.11 | (pre cont minus L1 minus L2 minus L3) x 1.25
Stretch at 15 percent contingency on award | 10.38 | 7.46 | Same base x 1.15, at controlled basis of estimate
Against the $9.24M priced allowance | 2.04 | 0.23 | Credible package minus allowance; stretch Option 2 sits below it
Kit ownership lever retained as a threshold test: buy below about $320,000 per front against the hire plus standby breakeven; fabrication drawings exist.

## BaseMenu
MARINE BASE CONCEPTS, each carried with its own cycle and availability assumption
Access totals AUD millions with 25 percent contingency. Net is against the reported case for the same option. Wet season fleet lay up care is retained in every concept; the change register records this recharacterisation.
Concept | Opt 1 total | Opt 1 net | Opt 2 total | Opt 2 net | Fleet / finish effect | Cycle and availability basis; what must be true
C0 Reported case: manned jack up as static base, whole campaign | 16.04 | 0 | 14.22 | 0 | 8 / 5 fronts; finish 11 Oct 2028 (Option 1), 9 Oct 2028 (Option 2) | Services afloat; fixed availability 0.90; ABH written reconciliation in progress
C1 Moored spud flat top, whole campaign, same services | 12.26 | 3.78 | 10.46 | 3.76 | Fleet unchanged; finish unchanged | Written spud quote at or near $3,000 per day; boarding in weather risk carried as sensitivity
C2 Zone phased: jack up through season one (Zone 3), deck serviced season two (Zones 2 and 1), fleet held | 14.68 | 1.36 | 12.74 | 1.48 | Fleet held; finish about 23 Oct 2028, float 9 days | Season two fixed availability derated 0.90 to 0.82 for shore servicing; one powered welfare set on deck; wet fleet care retained
C2+ Zone phased with one added season two front, date held | 14.56 | 1.48 | 12.49 | 1.73 | One extra front season two; finish about 4 Oct 2028 | As C2 with the season two rate restored by fleet
C2a Zone phased on a spud flat top in season one | 13.08 | 2.96 | 11.14 | 3.08 | As C2 | As C2 plus the written spud quotation
C3 Self sufficient fronts: powered set per front added for resilience | 18.59 | -2.55 | 15.8 | -1.58 | Fleet unchanged | Adds contract items 4.2.2, 4.2.4, 4.2.6 per front; pairs with C2 season two or C6
C4 Wharf deck service train | POA |  | POA |  | Roadway movements return | Welfare, stores and davit handling from the deck; priced on STL confirmation of laydown and power points
C5 Dry hire moored deck | POA |  | POA |  | As C1 | Whether a bargemaster requirement attaches to a moored flat top; marine authority position at HP5
C6 No marine base at all | 12.49 | 3.55 | 11.29 | 2.93 | 9 / 6 fronts; fixed availability falls to 0.82 | Crew transit arithmetic: about 12 minutes each way plus crib runs, about 58 minutes per 10 hour shift, an 8 percent derate; services queue on the 8 tonne roadway
Counterweight: one work front costs about $0.27M per season in kit and crane share plus fabrication against the $320,000 buy or hire breakeven. A concept that costs the campaign two fronts returns most of its saving.
Gross figures before per concept cycle adjustment (working brief ED-018-2026-08): C1 $3.76M, C2 $3.09M, C2a $4.68M. The nets above apply the season two availability derate and retained fleet care.