## 00 Read Me
STL Lucinda Jetty Access Options - Productivity and Cost Model
ED-018-2026-07 Rev A ¦ Concept-stage working model ¦ Commercial in confidence
Purpose | Activity-based comparison of the current scaffold delivery method and the proposed marine-side modular platform concept. Sourced facts, client-provided data, engineering assumptions and supplier inputs are kept separate.
Status | Draft for internal Endura/STL discussion. Not for construction, procurement or contractual reliance. Supplier rates and the current STL bent register are not commercially or technically closed.
Comparison discipline | The 0.36/week current figure is a claimed safe-access stage equivalent per calendar week. Proposed rates are modelled QA-closed bents per production week. These unlike measures are not divided to claim an uplift.
Stress test | 227 bents / 60 nominal production weeks = 3.783 completed bents/week. The 227-bent quantity is a conservative whole-scope stress case pending the priority and closeout register.
Commercial basis | Yellow rates are editable working allowances, not supplier quotations. A structured GGC monetary quotation was not identified in the supplied folder. Raw OCR evidence is preserved on the GGC Evidence sheet.
Colour convention | Yellow = editable assumption or rate. Blue = source-derived or formula result. Red = unresolved/not modelled. Green = verified/accepted input.
Required use | Update supplier and client inputs first. Then review Proposed Cycle, Fleet Productivity, Programme, Cost Build-Up and Dashboard. Do not issue a completion or cost commitment while red gates remain open.

## 01 Source Register
Source Register and Evidence Classification
Primary files from the organised Drive package and attached concept presentation.
ID | Source / file | Type | Use | Evidence class | Review status | Material limitation | Location
S01 | ED-018-2026-01 STL Method Assessment Proposal Rev A | Proposal | Scope, promised deliverables and evaluation basis | Project evidence | Reviewed | Concept assessment excludes detailed engineering | Drive / Proposal
S02 | AAB Contract Scope & Specification, pages 1-407 | Executed contract pack | Scope, quantities, specifications, pricing and obligations | Project evidence | Reviewed for applicable sections | Commercial trace must be rechecked before external issue | Drive root
S03 | Schedule.pdf and June 2026 programme screenshots | Programme | Current planned sequence and durations | Client-provided | Reviewed | Native MPP links, calendars, float and critical path not independently verified | Drive root
S04 | AAB Claim Qty's.xlsx | Claim extract | March-July 2026 claimed stage quantities and weld actuals | Client-provided | Recomputed | Parent progress workbook/certification lineage unavailable | Drive / AAB current progress
S05 | SCMC-22020-REP-001 Rev 1 | Strategy report | Asset condition, constraints and acceleration options | Project evidence | Reviewed | Predates current execution data | Drive / Summary report
S06 | July 2026 JPHR inspection reports | Site reports | Access, weather, workfront and quality observations | Client-provided | Reviewed | Not a complete lost-time dataset | Drive / Site reports
S07 | Drawing Package.pdf | Drawings | Bent families, geometry, levels and interfaces | Project evidence | Reviewed at concept level | Temporary-works capacity remains design scope | Drive / Drawing
S08 | Annual ship loading profile screenshot | Operations | Shipping frequency/interface | Client-provided | Reviewed | Future call dates not supplied | Drive / Ship profile
S09 | GGC platform drawings, photos, workboat, lift plan and methodology precedent | Supplier precedent | Platform geometry, flotation, winch/lift precedent and workboat capability | Supplier evidence | Reviewed | Does not certify the proposed Lucinda configuration or price | Drive / Floating Panel and GGC folders
S10 | Lucinda Marine Access Concept Discussion.pptx | Concept reference | Zones, spread, execution concept and key questions | Engineering concept | Reviewed | Contains discussion assumptions, not approved design | Attached
S11 | STL bent closeout / priority register | Required client input | Remaining scope, family mix, priority and preservation | Open | Not supplied | Scope, programme and cost cannot be finalised | RFI
S12 | Bathymetry, seabed and metocean | Required client input | JUB feasibility, moored transition and operability | Open | Not supplied | Marine concept remains conditional | RFI
S13 | GGC / JUB / containment commercial quotation | Required supplier input | Supplier rates and availability | Open | No structured monetary quote verified | Cost model uses editable allowances | RFI

## 02 Assumptions
Model Assumptions and Control Inputs
Yellow cells are editable. None of the yellow inputs should be presented as verified facts.
ID | Category | Input | Value | Unit | Basis | Status
A001 | Scope | Whole-scope stress-case bents | 227 | bents | Endura stress case pending STL register | Open
A002 | Programme | Nominal production seasons | 2 | seasons | 2027 and 2028 dry seasons | Assumption
A003 | Programme | Nominal production weeks per season | 30 | weeks | Working basis; dated calendar to replace | Assumption
A004 | Calendar | Working days per week | 6 | days | Single-shift base model | Assumption
A005 | Calendar | Residual stochastic availability | 85% | factor | Weather and breakdown only, after explicit blocks | Assumption
A006 | Shift | Hours per shift | 10 | hours | Single-shift base | Assumption
A007 | Production | Weld quantity per typical bent equivalent | 52.56 | lm | 473.025 lm / 9 inspection equivalents | Client data
A008 | Production | Repair approval hold | 3 | shifts | One bent-level submission assumption | Assumption
A009 | Production | Active coating work | 1.5 | shifts | Excludes elapsed wash/dry/recoat holds | Assumption
A010 | Production | Platform relocation package | 11 | hours/bent | Advance rigging share + lower/tow/hook/tower/services | Assumption
A011 | Shipping | Ship calls per year | 12 | calls/year | Midpoint of 10-14 client range | Client data
A012 | Shipping | Make-safe allowance per call | 2 | days | Contract/client basis | Project fact
A013 | Scope | Original firm bents | 237 | bents | 212 typical + 13 anchor + 10 passing variants + 2 specials | Project fact
A014 | Scope | Optional expansion-joint bents | 20 | bents | Executed contract option | Project fact

## 03 Current Baseline
Current Delivery Method - Plan and Demonstrated Stage Output
Planned completed-bent output and claimed payment-stage output are shown separately.
Metric | Mar | Apr | May | Jun | Jul | Total | Normalised rate | Evidence / limitation
Safe access equivalent | 0.5 | 2.5 | 0 | 3.2 | 1.7 | 7.9 | 0.36073 | Claimed payment-stage quantity; not a QA-closed bent
Inspection / UT equivalent | 0 | 5 | 0 | 2 | 2 | 9 | 0.41096 | Claimed payment-stage quantity; not a QA-closed bent
Blast / coating equivalent | 0 | 0 | 0 | 3.5 | 3.5 | 7 | 0.31963 | Claimed payment-stage quantity; not a QA-closed bent
Denso jacket pile equivalent | 1.32 | 3.34 | 0 | 0 | 7.34 | 12 | 0.54795 | Claimed payment-stage quantity; not a QA-closed bent
Keeper angles | 0 | 0 | 0 | 10 | 6 | 16 | 0.73059 | Claimed payment-stage quantity; not a QA-closed bent
8 mm weld prep / weld, lm | 0 | 0 | 0 | 89.5 | 94.36 | 183.86 | 8.3954 | Claimed payment-stage quantity; not a QA-closed bent
10 mm weld prep / weld, lm | 0 | 0 | 0 | 112.3 | 176.865 | 289.165 | 13.2039 | Claimed payment-stage quantity; not a QA-closed bent
Programme summary
Metric | Value | Unit | Basis | Assurance note
Programme bents | 257 | bents | Validated extraction matching supplied screenshots | Includes six finishes in 2025 and 251 in 2026-2028
First programmed start | 2025-11-03 | date | Schedule extraction | Native MPP logic not independently verified
Last programmed finish | 2028-12-02 | date | Schedule extraction | Subject to calendar/shutdown logic
Elapsed calendar duration | 161 | weeks | Recomputed | Approximate
Planned shutdown periods | 56.6 | weeks | Three major gaps | 135, 125 and 136 days
Net programme production weeks | 104.4 | weeks | Elapsed less major shutdowns | Calendar basis
Planned in-season completion rate | 2.4617 | bents/week | Programme-level calculation | Approximately 2.46 completed bents/week
Typical programmed cycle | 14.5 | days | Common/median typical duration | Typical rows generally 14-15 days
Mean programmed duration | 16.7 | days | All families | Includes special/EJ rows
Peak concurrent WIP | 9 | bents | Programme extraction | Not equal to nine scaffold sets
Physical scaffold sets observed | 4 | sets | Execution records | Four sets did not mean four continuously usable fronts
Claimed safe-access stage rate | 0.36073 | equiv/week | Claim extract | Not QA-closed bents
Typical current cycle
Stage | Duration | Unit | Character | Constraint | Source | Confidence
Scaffold erection and encapsulation | 2 | days | Access handling | Roadway, weather, volumetric hire | Schedule / contract | Medium
Wash, inspection and UT | 1 | days | Productive | Lower access availability | Schedule | Medium
Repair approval hold | 3 | days | Waiting | Access remains occupied | Schedule | Medium
Weld repairs | 2 | days | Productive, variable | Repair growth and workfront availability | Schedule / claims | Low-Medium
Blast and two coats | 3 | days | Productive + elapsed | Containment, recoat, weather | Schedule / G01 | Medium
Pile jackets | 0 | days | Tide-limited | Scope varies by bent | Schedule | Low
Scaffold dismantle / relocation | 1 | days | Access handling | Roadway / weather | Schedule | Medium
Sundays / extra allowance | 2.5 | days | Calendar | Programme conventions vary | Endura reconciliation | Low-Medium

## 04 Proposed Cycle
Proposed Marine Access Cycle - Activity Build-up
Active work, elapsed holds, access-set occupancy and unmodelled work are separated.
Seq | Activity | Zone | Active shifts | Elapsed hold | Set occupancy | Resource basis | Status | Evidence / assumption | Acceptance basis | Cost driver
1 | Advance rigging package share | Next bent | 0.4 | 0 | 0.4 | Advance rigging crew | Modelled | 4 h share/bent | Timed installation, proof test and removal | Rigging
2 | Lower completed platforms | Current bent | 0.1 | 0 | 0.1 | Platform crew | Modelled | 1 h allowance | Controlled lowering proven | Platform/workboat
3 | Tow to next bent | Marine move | 0.2 | 0 | 0.2 | Workboat | Modelled | 2 h allowance | Defined sea-state/tow limit | Workboat
4 | Position, hook-on and winch | New bent | 0.2 | 0 | 0.2 | Rigging/platform crew | Modelled | 2 h allowance | Timed lift, level and restraint | Platform/rigging
5 | Move access tower | New bent | 0.1 | 0 | 0.1 | JUB crane crew | Modelled | 1 h allowance | Crane/clump-weight method proven | JUB
6 | Traversing decks and services | New bent | 0.1 | 0 | 0.1 | Platform crew | Modelled | 1 h allowance | Temporary-works design and timed cycle | Platform/services
7 | Wash, inspect and UT | Whole bent | 0.5 | 0 | 0.5 | Inspection team | Modelled | Concept allowance | Accepted inspection dossier | Labour
8 | Diagnostic blast, two pile bands | Piles | 1 | 0 | 1 | Blast team | Modelled | Approx. 27-29 m²; conservative lot allowance | Profile/cleanliness/environment accepted | Blast plant
9 | Headstock enclosure and diagnostic blast | Headstock | 0 | 0 | 0 | Containment/blast team | NOT MODELLED | Supplier concept required | Measured accepted cycle | Containment
10 | Mark-up and repair definition | Whole bent | 0.5 | 0 | 0.5 | Inspection/engineer | Modelled | Both piles/headstock before submission | Approved mark-up pack | Engineering
11 | Repair approval hold | Whole bent | 0 | 3 | 3 | Reviewer | Modelled assumption | One bent-level submission, subject to approval | Turnaround achieved | Set occupancy
12 | Weld repairs and NDT | Whole bent | 4.42 | 0 | 4.42 | 2 crews at 6 lm/crew-shift | Modelled | 52.56 lm/bent equivalent | Accepted output incl. rework | Weld crews
13 | Post-weld final preparation | Active work lots | 1 | 0 | 1 | Blast/prep team | Modelled | Local preparation allowance | Coating hold point accepted | Blast plant
14 | Coating active work and QA | Pile/headstock lots | 1.5 | 0 | 1.5 | Coating team | Modelled active work | Stripe coats and QA included | G01/Dulux/ITP acceptance | Coating
15 | Coating wash/dry and recoat elapsed holds | Pile/headstock lots | 0 | 0 | 0 | No active crew | NOT MODELLED | 14 h min, 14 d max; work-lot logic open | Trial elapsed cycle | Set occupancy
16 | Petrolatum jacket, accessible tidal band | Piles | 0.5 | 0 | 0.5 | 3-person jacket crew | Modelled | Below-LAT excluded | Timed accepted pile cycle | Jackets
17 | Jacket installation below LAT | Piles | 0 | 0 | 0 | Marine/jacket team | NOT MODELLED | Lower termination/method unresolved | Manufacturer and trial acceptance | Marine
18 | Containment moves / changeover | Bent | 0.5 | 0 | 0.5 | Containment crew | Modelled | Half-shell movement allowance | Timed close/open/reposition | Containment
19 | Clean-out, QA holds and rework | Bent | 0 | 0 | 0 | Multi-trade | NOT MODELLED | Proving data required | Measured closeout duration | Multi-trade
MODELLED TOTAL

## 05 Fleet Productivity
Fleet and Productivity Sensitivity
Fleet counts are diagnostics, not procurement recommendations. Missing work increases cycle time.
Scenario | Description | Cycle days/set | Sets | Days/week | Residual availability | Rate, bents/week | Weeks for 227 | Meets 60 weeks? | Weld crews/set | Total weld crews
S1 | Base: 2 weld crews/set at 6 lm/crew-shift, one 3-day bent-level approval hold | 14.02 | 11 | 6 | 85% | 4.0014 | 56.7298 | YES | 2 | 22
S2 | 4 weld crews/set at 8 lm/crew-shift, full approval hold | 11.26 | 9 | 6 | 85% | 4.0764 | 55.6867 | YES | 4 | 36
S3 | S2 plus no routine approval hold under accepted repair library/delegation | 8.26 | 7 | 6 | 85% | 4.322 | 52.5216 | YES | 4 | 28
S4 | 6 weld crews/set at 10 lm/crew-shift, no routine approval hold | 7.48 | 6 | 6 | 85% | 4.0909 | 55.4889 | YES | 6 | 36
Sets sensitivity
Sets | S1 base | S2 | S3 | S4 | Stress target | Base weeks | Comment
2 | 0.72753 | 0.90586 | 1.2349 | 1.3636 | 3.7833 | 312.0137 | Diagnostic only
3 | 1.0913 | 1.3588 | 1.8523 | 2.0455 | 3.7833 | 208.0092 | Diagnostic only
4 | 1.4551 | 1.8117 | 2.4697 | 2.7273 | 3.7833 | 156.0069 | Diagnostic only
5 | 1.8188 | 2.2647 | 3.0872 | 3.4091 | 3.7833 | 124.8055 | Diagnostic only
6 | 2.1826 | 2.7176 | 3.7046 | 4.0909 | 3.7833 | 104.0046 | Diagnostic only
7 | 2.5464 | 3.1705 | 4.322 | 4.7727 | 3.7833 | 89.1468 | Diagnostic only
8 | 2.9101 | 3.6234 | 4.9395 | 5.4545 | 3.7833 | 78.0034 | Diagnostic only
9 | 3.2739 | 4.0764 | 5.5569 | 6.1364 | 3.7833 | 69.3364 | Diagnostic only
10 | 3.6377 | 4.5293 | 6.1743 | 6.8182 | 3.7833 | 62.4027 | Diagnostic only
11 | 4.0014 | 4.9822 | 6.7918 | 7.5 | 3.7833 | 56.7298 | Base meets target
12 | 4.3652 | 5.4352 | 7.4092 | 8.1818 | 3.7833 | 52.0023 | Base meets target

## 06 Resources
Resource Build-up by Scenario
Transparent planning allowances. Safe simultaneous work zones remain a proving-campaign gate.
Resource | Unit | S1 | S2 | S3 | S4 | Basis | Confidence | Key limitation
Weld crews, 2 persons | crew | 22 | 36 | 28 | 36 | Sets × crews/set | Low-Medium | Safe simultaneous weld zones not proven
Blast/coating crews | crew | 11 | 9 | 7 | 6 | 1 per active set | Low | Zoning and recoat logic open
Inspection/UT teams | team | 6 | 5 | 4 | 3 | Shared at 0.5 team/set | Medium | Advance screening does not replace diagnostic blast
Containment/platform crews | crew | 11 | 9 | 7 | 6 | 1 per set | Low | Supplier handling method open
Advance rigging crews | crew | 3 | 3 | 2 | 2 | Shared ahead of front | Low-Medium | Proof-test cycle open
Jacket crews, 3 persons | crew | 6 | 5 | 4 | 3 | Shared at 0.5 crew/set | Low | Below-LAT method open
JUB marine crew | person | 4 | 4 | 4 | 4 | Bargemaster/crane/deck support | Low | Unit not selected
Workboat master/deckhand | person | 2 | 2 | 2 | 2 | One workboat | Medium | Separate rescue craft may be required
Project management/engineering | person | 6 | 6 | 6 | 6 | Campaign core | Medium | Contractor organisation to confirm
HSE/QA/environmental | person | 6 | 6 | 5 | 5 | Scales with workfronts | Low-Medium | Final SIMOPS and monitoring open

## 07 Rate Inputs
Commercial Rate Inputs
Yellow values are editable working allowances, not supplier quotations. Replace before any external commercial issue.
ID | Cost item | Type | Unit | Qty basis | Rate, AUD ex GST | Source class | Status | Source / limitation | Contingency
R001 | Detailed engineering, RPEQ design and independent check | Fixed | campaign | 1 | 500000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 15%
R002 | Platform / winch adaptation, certification and proof-load equipment | Fixed per set | set | 1 | 200000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 20%
R003 | Traversing decks and access tower package | Fixed per set | set | 1 | 100000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 20%
R004 | Pile half-shell containment, extraction interface and sealing | Fixed per set | set | 1 | 100000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 25%
R005 | Headstock containment module allowance | Fixed per set | set | 1 | 150000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 30%
R006 | Marine spread mobilisation and demobilisation | Fixed | campaign | 1 | 800000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 25%
R007 | Proving campaign, instrumentation and engineering closeout | Fixed | campaign | 1 | 300000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 20%
R008 | Permits, marine assurance, environmental plans and insurance studies | Fixed | campaign | 1 | 150000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 25%
R009 | JUB / support barge and service base | Time | week | 1 | 35000 | Specialist working range translated to weekly basis | Working input | Replace with supplier quote where applicable | 25%
R010 | Workboat / multicat / rescue craft | Time | week | 1 | 10000 | Endura allowance pending GGC commercial quote | Working input | Replace with supplier quote where applicable | 20%
R011 | Project management, engineering, planning and supervision | Time | week | 1 | 55000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 20%
R012 | Accommodation, travel and local transport | Time | week | 1 | 35000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 25%
R013 | Power, compressed air, breathing air, wash water and fuel | Time | week | 1 | 25000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 25%
R014 | Base maintenance, spares and campaign consumables | Time | week | 1 | 15000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 25%
R015 | Platform set hire / ownership recovery | Set-time | set-week | 1 | 7500 | Endura allowance pending GGC commercial quote | Working input | Replace with supplier quote where applicable | 30%
R016 | Winch, rigging and temporary-works inspection / maintenance | Set-time | set-week | 1 | 2000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 25%
R017 | Containment, extraction and vacuum-recovery plant | Set-time | set-week | 1 | 4000 | Endura allowance pending supplier quote | Working input | Replace with supplier quote where applicable | 30%
R018 | Weld repairs, including prep, fit, weld, NDT and ordinary rework | Variable | lm | 52.5583 | 350 | Endura working allowance | Working input | Replace with supplier quote where applicable | 30%
R019 | Blast / coating production consumables and QA | Variable | bent | 1 | 8000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 25%
R020 | Petrolatum jacket material and installation | Variable | bent | 1 | 5000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 30%
R021 | Hazardous coating waste, transport and disposal | Variable | bent | 1 | 2000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 35%
R022 | Digital QA dossier and closeout engineering | Variable | bent | 1 | 2000 | Endura working allowance | Working input | Replace with supplier quote where applicable | 20%

## 08 Cost Build-Up
Indicative Cost Build-up by Productivity Scenario
Working parametric estimate only. Current supplier rates are not commercially closed.
Cost category | Basis | S1 | S2 | S3 | S4 | Evidence status | Sensitivity | Current reference | Comment
Fixed engineering, proving and assurance | R001 + R007 + R008 | 1122500 | 1122500 | 1122500 | 1122500 | Allowance | Medium | n/a | One campaign
Platform, winch, traversing deck and containment packages | Sets × R002:R005 | 7480000 | 6120000 | 4760000 | 4080000 | Allowance | High | n/a | Scales directly with set count
Marine mobilisation / demobilisation | R006 | 1000000 | 1000000 | 1000000 | 1000000 | Allowance | High | n/a | Candidate spread pending
Campaign time-related cost | Campaign weeks × R009:R014 | 12225265.0624 | 12000486.0566 | 11318398.0392 | 11957855.5556 | Allowance | High | n/a | Programme driver
Set-related weekly cost | Weeks × sets × R015:R017 | 10889279.0196 | 8745597.8431 | 6415509.6078 | 5809686.6667 | Allowance | High | n/a | Fleet-size driver
Weld production | 227 × 52.56 lm × R018 | 5428487.4583 | 5428487.4583 | 5428487.4583 | 5428487.4583 | Allowance | High | Rate-only baseline | Repair quantity sensitive
Blast, coat, jackets, waste and QA | 227 × R019:R022 | 4903200 | 4903200 | 4903200 | 4903200 | Allowance | Medium | Current blast/coat contract line reference | Scope sensitive
Subtotal before model contingency | Sum above | 43048731.5403 | 39320271.3581 | 34948095.1054 | 34301729.6806 | Formula |  | Current access basis + tooling ~AUD 9.275M | Not like-for-like
Model contingency | 20% | 8609746.3081 | 7864054.2716 | 6989619.0211 | 6860345.9361 | Formula | High | n/a | Concept maturity
Indicative campaign total | Subtotal + contingency | 51658477.8484 | 47184325.6297 | 41937714.1265 | 41162075.6167 | Formula |  | n/a | Not a quotation
Indicative cost per stress-case bent | Total / 227 | 227570.387 | 207860.4653 | 184747.6393 | 181330.7296 | Formula |  | Current access basis ~AUD 39k / firm bent | Different scope basis

## 09 Programme
Indicative Implementation Programme
Known calendar blocks are explicit. A dated bent-level line of balance remains a gate.
Phase | Start | Finish | Calendar days | Production effect | Basis | Status | Owner | Required output | Notes
Supplier development and concept design | 2026-09-01 | 2026-11-30 | 91 | No production | Stage 1 roadmap | Assumption | STL/Endura | Selected system and design basis | Supplier data/RFIs
RPEQ temporary works and independent check | 2026-10-01 | 2027-01-31 | 123 | No production | Concept roadmap | Assumption | Delivery contractor | Certified platform/suspension/access designs | Can overlap procurement
Fabrication / modification / FAT | 2026-11-01 | 2027-02-28 | 120 | No production | Concept roadmap | Assumption | Supplier | Completed sets and FAT records | Lead time to confirm
Mobilisation and site establishment | 2027-03-01 | 2027-03-28 | 28 | Ramp-up | Concept roadmap | Assumption | Contractor | JUB/workboat/sets established | Subject to marine availability
Proving campaign | 2027-03-29 | 2027-04-25 | 28 | Restricted production | Acceptance-gate basis | Assumption | Contractor/STL | Measured cycles and frozen model | Recommended first 3-5 representative bents
2027 production season | 2027-04-26 | 2027-11-30 | 219 | Production | Dry-season basis | Assumption | Contractor | Line-of-balance production | Known outages/ship calls inserted later
Wet-season demobilisation | 2027-12-01 | 2028-03-15 | 106 | No production | Client basis | Client-provided | Contractor | Fleet recovered/refurbished | Cyclone plan required
2028 remobilisation | 2028-03-16 | 2028-04-05 | 21 | Ramp-up | Working allowance | Assumption | Contractor | Re-established fronts
2028 production season | 2028-04-06 | 2028-11-30 | 239 | Production | Dry-season basis | Assumption | Contractor | Priority works complete | Target subject to register
Scenario capacity before missing work and dated losses
Scenario | Rate/week | Nominal weeks | Nominal capacity | Stress quantity | Margin | Assurance note
S1 | 4.0014 | 60 | 240.0856 | 227 | 13.0856 | Before unmodelled activities and explicit calendar losses
S2 | 4.0764 | 60 | 244.5826 | 227 | 17.5826 | Before unmodelled activities and explicit calendar losses
S3 | 4.322 | 60 | 259.322 | 227 | 32.322 | Before unmodelled activities and explicit calendar losses
S4 | 4.0909 | 60 | 245.4545 | 227 | 18.4545 | Before unmodelled activities and explicit calendar losses

## 10 MCA
Multi-Criteria Assessment
Concept-stage scores for workshop discussion. Scores are not a substitute for supplier evidence.
Criterion | Weight | Current scaffold | JUB direct workface | Modular/spud pontoon | Suspended floating platforms + JUB | Marine rope access | Hybrid | Rationale | Maturity
Productivity / scalability | 20% | 2 | 3 | 3 | 4 | 2 | 4 | Serial scaffold cycle versus reusable/multiple fronts | Concept
Weather resilience | 10% | 2 | 4 | 2 | 4 | 1 | 4 | Lifted deck reduces direct tide/heave exposure; wind remains | Concept
Tide independence | 8% | 1 | 5 | 2 | 4 | 1 | 4 | Below-LAT scope remains dependent | Concept
Environmental containment | 12% | 3 | 4 | 3 | 4 | 2 | 4 | Reusable local containment requires proving | Concept
Structural / seabed interfaces | 8% | 3 | 1 | 4 | 2 | 4 | 3 | Hung points need RPEQ; JUB needs bathymetry/seabed | Concept
Roadway / terminal interference | 10% | 1 | 4 | 4 | 4 | 4 | 4 | Marine logistics removes bulk supply from single lane | Concept
Shipping make-safe | 7% | 3 | 2 | 3 | 3 | 4 | 3 | All methods require defined response | Concept
Cyclone recovery | 8% | 3 | 1 | 3 | 2 | 4 | 3 | Full spread recovery remains a gate | Concept
Safety in design / rescue | 7% | 3 | 4 | 3 | 2 | 2 | 3 | Suspended access/rescue not demonstrated at all levels | Concept
Mobilisation / availability | 5% | 4 | 1 | 3 | 3 | 4 | 3 | JUB and bespoke containment lead times | Concept
Cost confidence | 3% | 4 | 1 | 2 | 1 | 3 | 2 | Supplier quotations incomplete | Concept
Approvals / insurance | 2% | 4 | 1 | 2 | 2 | 3 | 3 | Marine methods need regulator/insurance positions | Concept
Weighted scores
| Current scaffold | JUB direct | Modular pontoon | Suspended + JUB | Rope access | Hybrid
| 2.44 | 2.96 | 2.95 | 3.29 | 2.63 | 3.57

## 11 Proposal Compliance
ED-018-2026-01 Deliverable Compliance Matrix
Tracks every core Stage 1 commitment to a section and evidence status.
Proposal commitment | Response in report/model | Status | Evidence / file | Gap / action before issue | Owner | Acceptance
Review contract, specification, methodology and programme | Report Sections 3-5; workbook Current Baseline and Source Register | Addressed | Contract, Schedule.pdf, claim workbook, site reports | Native MPP logic and current bent register remain open | Endura/STL | Sources reconciled
Confirm constraint envelope | Report Section 4; Risk/RFI register | Partially addressed | Drawings, Shoreline, contract, ship profile | Bathymetry, metocean, approvals and insurer positions | STL/Endura | Constraint register accepted
Identify and screen candidate access methods | Report Section 6; MCA sheet | Addressed | Proposal longlist and source evidence | Workshop confirmation | Endura/STL | Shortlist agreed
Develop shortlisted concepts | Report Sections 7-10; Proposed Cycle | Partially addressed | Concept methodology and GGC precedent | Supplier design and bent-family plates | Endura/suppliers | Concept design basis accepted
Define deployment and relocation cycle | Report Sections 8-9; Proposed Cycle | Partially addressed | 11 h working package | Timed proving campaign required | Contractor | Accepted measured cycle
Assess tide/weather operability | Report Sections 4, 9 and 12 | Partially addressed | Specialist assumptions | Site records/activity-specific limits | Marine contractor | Operability model accepted
Define containment and waste approach | Report Sections 8 and 10 | Partially addressed | Half-shell concept | Headstock enclosure and mass balance | Supplier | Containment trial accepted
Define marine logistics, materials, waste and crew movement | Report Section 9 | Addressed at concept level | JUB/workboat concept | Unit layout and service umbilicals | Marine contractor | Layout accepted
Assess structural interfaces and loading | Report Section 11 | Open design gate | Drawings/GGC precedent | RPEQ design and independent check | TW designer | Certified design
Define cyclone and shipping response | Report Section 12 | Partially addressed | 2-day make-safe and demob concept | Timed full-spread drill and forecast dates | Contractor/STL | Response plan accepted
Multi-criteria assessment | Report Section 13; MCA sheet | Addressed | Concept scoring | STL workshop agreement | Endura/STL | Scores agreed
Indicative programme comparison | Report Section 14; Programme sheet | Addressed with qualifications | Schedule and productivity model | Dated line of balance | Planner | Programme accepted
Indicative cost comparison | Report Section 15; Cost Build-Up | Structured, not commercially closed | Contract access basis and allowances | Supplier quotations and bent register | Commercial | One reconciled cost truth
Market soundings | Report Section 16; Source Register | In progress | GGC evidence received | Firm GGC/JUB/containment quotations | Endura | Market evidence recorded
Options workshop | Report Section 17 | Pending | Workshop agenda included | Hold workshop | STL/Endura | Decision recorded
Recommended methodology and implementation roadmap | Report Sections 18-19 | Addressed conditionally | Preferred concept and gate roadmap | Close key feasibility gates | STL/Endura | Direction approved

## 12 Risks & RFIs
Open Risks, Verification Gates and RFIs
No missing supplier or client input is silently treated as resolved.
ID | Priority | Risk / gate | Required evidence | Consequence if unresolved | Owner | Due | Status | Closure
OI-01 | Critical | Current bent closeout and priority register | Bent-by-bent status, family, preservation, priority and method assignment | Scope, programme and cost cannot be finalised | STL | Immediate | Open
OI-02 | Critical | Bathymetry and seabed | Survey, leg-bearing and/or mooring basis | JUB feasibility and inshore transition remain open | STL/marine contractor | Before concept freeze | Open
OI-03 | Critical | Platform mass, buoyancy and CoG | Certified load schedule with people, containment, waste and retained water | Hoist/hang-off design cannot proceed | GGC/supplier | Before TW design | Open
OI-04 | Critical | Sliding suspension and winch control | Travel, locking, man-riding status, fault cases and lowering | Platform cannot safely follow rake | GGC/TW designer | Before proving | Open
OI-05 | Critical | Traversing-deck design | Load path, relative movement, travel, locking and edge protection | 360° access unproven | Supplier/TW designer | Before proving | Open
OI-06 | Critical | Pile and headstock containment | Geometry, seals, extraction, negative pressure, wind limit, recovery and cycle | Environmental/productivity case incomplete | Containment supplier | Before proving | Open
OI-07 | Critical | Below-LAT jacket method | Submerged installation, lower termination and inspection method | Scope/cycle incomplete | Manufacturer/marine specialist | Before model freeze | Open
OI-08 | High | Coating elapsed cycle | Written G01/Dulux sequence and timed trial | Set occupancy understated | Coating supplier/contractor | Proving | Open
OI-09 | High | Bent-level approval workflow / repair library | One-submission workflow, delegation and exceptions | Approval holds may multiply | STL/reviewing engineer | Before procurement | Open
OI-10 | High | Accepted weld output / simultaneous zones | Timed shift data incl. prep, NDT and rework | Fleet/resource sizing uncertain | Welding contractor | Proving | Open
OI-11 | High | JUB unit, reach and relocation | Candidate unit, crane chart, coverage, move time and refuge | Marine programme/cost uncertain | Marine contractor | Market sounding | Open
OI-12 | High | Metocean and operational limits | Site data and activity-specific limits | Availability remains assumption | STL/marine contractor | Before final programme | Open
OI-13 | High | Shipping forecast / make-safe | FY27-28 forecast and permitted continuing work | Calendar provisional | STL | Before final programme | Open
OI-14 | High | Regulatory, biosecurity and insurance | GBRMPA, MSQ, PoT, EPA, vessel and insurance positions | Approvals/tender scope incomplete | STL/advisers | Before tender | Open
OI-15 | High | Supplier commercial quotations | Firm rates, inclusions and availability | Cost model not commercially closed | GGC/JUB/containment | Immediate | Open

## 13 Dashboard
Executive Dashboard
Decision summary for the options workshop. Commercial values are working allowances only.
Stress-case bents |  |  | Required rate |  |  | Current planned in-season rate |  | Claimed safe-access stage rate
227 |  |  | 3.7833 |  |  | 2.4617 |  | 0.36073
Scenario | Cycle days | Sets | Rate/week | Weeks | Indicative total | Cost/bent | Interpretation
S1 | 14.02 | 11 | 4.0014 | 56.7298 | 51658477.8484 | 227570.387 | Nominally fits 60 weeks before missing work
S2 | 11.26 | 9 | 4.0764 | 55.6867 | 47184325.6297 | 207860.4653 | Nominally fits 60 weeks before missing work
S3 | 8.26 | 7 | 4.322 | 52.5216 | 41937714.1265 | 184747.6393 | Nominally fits 60 weeks before missing work
S4 | 7.48 | 6 | 4.0909 | 55.4889 | 41162075.6167 | 181330.7296 | Nominally fits 60 weeks before missing work
Decision summary
1 | Current evidence | The current programme plans approximately 2.46 completed bents per production week. Claimed safe-access output is approximately 0.36 stage equivalents per calendar week. They are not directly comparable.
2 | Preferred direction | Suspended floating platforms with JUB logistics are the preferred concept for typical bents because they attack repeated scaffold handling, road congestion and tide-gated access.
3 | Programme reality | The whole-scope stress target is 3.783 completed bents/week. The incomplete model needs 11 sets in the base case and 6 in the strongest diagnostic case.
4 | Commercial reality | The cost framework is complete, but supplier rates and the current bent register are not. Totals are working allowances, not a quotation or budget commitment.
5 | Recommendation | Proceed to supplier design, RFIs and a proving campaign. Freeze the fleet, programme and commercial recommendation only after accepted trial data.

## 14 GGC Evidence
GGC Rate and Equipment Evidence Extract
Raw OCR evidence is retained for traceability. No OCR value is treated as a verified supplier quotation without source confirmation.
Source image | Currency-like OCR hits | OCR extract / note | Model treatment
No structured rate file identified | n/a | No OCR extract available. | All proposed rates remain editable Endura allowances