| REVIEWER BRIEFING PACK Lucinda Jetty Remediation Access Methodology Options Assessment Prepared for Mat Clenton for early operational review. marine civil / nearshore works Endura Decommissioning - Ref ED-018-2026-01 - 7 August 2026. Rev A |  |
| --- | --- |

How to use this pack:  we're two weeks into a fast options study for the asset owner and want your operational gut-check before we go deep. Read sections 1 to 6 for context, then hit Section 7 — the questions. Rough notes, voice memos or track changes all welcome; we need it early next week. Everything here is strictly confidential: live contract dispute, unlisted client sensitivities. Please don't forward or discuss outside Endura.

# 1   The project in one page

Sugar Terminals Limited (STL) owns the Lucinda Bulk Sugar Terminal in North Queensland, on the GBR coast between Townsville and Cairns. Raw sugar is exported over a 5.7 km jetty — the longest sugar jetty in the world — carrying a single-lane roadway and an enclosed conveyor gallery out to a berthing pocket. The structure is steel pilebents (steel headstock on raked steel piles) at ~24 m centres, roughly 237 bents, plus a 110-span gallery wrapping scope.

A multi-year remediation contract (AS 4000 construct-only, ~$25M) is on foot: weld repairs to corroded piles and headstocks, abrasive blast and recoat of headstocks (full encapsulation — coal tar epoxy removal beside the reef), and petrolatum jacket systems on the piles through the tidal zone. Work is delivered from the deck: kerb-hung scaffold built and stripped at every bent, two road-going gantry 'spiders' carrying weld and blast kit, everything fed down the single-lane roadway while the terminal keeps operating.

Endura is engaged by STL (GM Asset Management & Infrastructure) to run an independent access-methodology options assessment: could these works be delivered faster and safer from the marine side, and through what delivery model. Stage 1 is a 2-3 week desktop study now under way; outputs go to the owner's exec and board.

# 2   Why this matters now — the drivers

- A hard 2028 date. A 2022/23 asset integrity report requires the high-priority structural repairs closed out by 2028, or STL faces re-assessment and potentially quarantining the asset. The client regards 2028 as real, not conservative.

- The degradation is now visible. Measured deflection of the conveyor gallery — of the order of 10-20 mm across sections — around bent 280 and beyond, approaching the berthing pocket. Section loss is real and progressing, not just forecast.

- The contractor is far behind. Mobilised Sept 2025. Planned completion to end July 2026 was ~17%; actual is ~3.5-4%. Separable Portion 1 (highest risk) barely touched; SP2 roughly a third done. The contractor's own re-forecast programs land completion in 2031 — three years past the integrity deadline.

- Formal contract action is live. STL has the incumbent under a substantial breach process with a remedy deadline of 14 August; termination is a realistic outcome if the response isn't credible. STL doubts the economics of the incumbent's likely answer (more scaffold sets: 1 set grew to 4; 10 changes nothing). Treat this as highly sensitive — do not repeat outside the team.

- Safety and quality trouble too. An independent site review ~6 weeks ago found poor practice, principally around scaffolding, and quality concerns on welds and coatings — STL shut the site until controls were in place. Inefficient, unsafe and slow have arrived together.

# 3   Why the current method loses

The failure is method-shaped, not effort-shaped. From the contract program, a representative bent cycle runs ~16 working days, and about half of it is not trade work: ~3 days of scaffold erect/encapsulate/strip/relocate at every bent, and a ~3-day weld-approval hold with plant parked on the bent. Two spiders (one weld, one blast) form a single queue all bents wait through; weld quantities are expressly unknown, so weld growth stalls the whole line. Pile jacketing runs to ~1.7 m LAT and from fixed decks becomes a tide-window exercise. Access is the single largest line in the contract — roughly $9M of $25M.

Layered on top: an owner-mandated full demobilisation December-March each wet season (cyclone risk deemed intolerable at tender), 10-14 shipping events a year with a 2-day make-safe notice (no work in or around the galleries while a ship is on the berth), no weather-delay relief in the contract, and a live terminal running down the same single-lane roadway the method occupies. The gallery-wrapping scope is the wind-day fallback, but it's a minor quantum — it gets eaten quickly.

# 4   Operational parameters — the constraint envelope

Direct from the contract pack and this week's sessions with the client. These are the rules any method must live inside:

| Parameter | What we know |
| --- | --- |
| Tide / datum | Pile jackets to ~1.7 m LAT; spring range of order 3 m (to be confirmed against tidal planes). Fixed-deck work at the bottom of the band is tide-gated today. |
| Weather | SE trades through the dry season; blast, paint and wrap are wind-limited. No weather relief in the contract. Wave climate worsens seaward; a large sandbank on the southern side shelters roughly bents 1-150, with exposure and corrosion severity increasing beyond it toward the berth. |
| Season | Cyclone readiness 1 Nov - 30 Apr. Owner-mandated full demob December-March; remobilise early March, full production late March through November. Any plant must be securable or removable for cyclone response. |
| Shipping | 10-14 vessel calls/yr, mostly Jul-Dec, booked only ~3-4 months out; make-safe on 2 days' notice. During shipping: no work in/around galleries; roadway transit and laydown continue; other work fronts can keep running. STL is providing shipping history, FY27 nominated outages and current bookings. |
| Roadway | Single lane, one-way for anything bigger than a ute; ~5 passing/relief bays; 8 t vehicle limit; 964 kNm girder moment cap for any wheeled gantry; live terminal traffic must keep moving. The contract JMV/straddle concept was meant to keep the lane clear — in practice operations are being compromised. |
| Marine side | Tug harbour available for crew boat ops. Bathymetry and seabed bearing along the alignment unconfirmed — the key unknown for jack-up and floating plant. GBR Marine Park adjacency: full containment for blasting, coal tar epoxy removal is regulated waste, GBRMPA/MSQ/Port positions to be tested. |
| Structure | Corroded members; any hung or wheeled load needs RPEQ design plus independent check. Gallery already deflecting near the berth end — assume conservative allowable loads out there. |
| Night work | Production night work is out — risk-averse board, would not pass. But low-risk marine activities on the tide (e.g. barge/jack-up moves, cf. Hay Point practice) are considered acceptable and can be planned. |
| Services | No usable power along the jetty; hydrant water only; limited compressed air in the gallery. Assume marine method is self-sufficient for power/air. |
| Governance | Decision is internal for now: GM → CEO → board alignment on methodology, then normal procurement. Board is risk-averse with little marine construction experience — outputs must include a non-technical, visual telling of the story. |

# 5   The client's emerging delivery thinking

Working hypothesis from the GM (not yet a decision):

- Split the jetty by exposure. Push the incumbent (or a like-for-like) to the sheltered front end (~bents 1-150): simpler single-lift scaffold, lighter corrosion, minimal wave action, less operational interference. Let them finish that and 'move on with life'.

- New method for the hard half. A marine-side methodology for the exposed outer sections where weather kills fixed-access productivity — established for the 2027 season onward, delivering the balance in two nine-month seasons across 2027-28 (18 months of production) to hit the 2028 integrity date.

- Contracting models still open. Scenarios on the table: (a) keep incumbent on the easy scope only; (b) STL/PCM engages a marine access contractor as the backbone, with the incumbent de-scoped to blast-and-paint trade works, welding contractor brought in, scaffold contractor ad hoc; (c) consolidate everything with one new organisation; (d) hybrids in between. Our study is expected to make the method call first, then let the contracting answer follow.

# 6   Our study and the candidate methods

Stage 1 (2-3 weeks, running now): confirm the constraint envelope; screen a long list to a shortlist; develop each shortlisted method into a working concept (configuration, equipment, deployment and bent-to-bent relocation cycle, tidal and weather operability, containment, marine logistics, structural interfaces, cyclone and shipping response); evaluate against the envelope with an indicative program and cost comparison against the scaffold baseline; sound out suppliers and contractors; report with a recommendation. We're building an integrated staged schedule — marine fronts flexing to gallery work when wind is up, shipping placeholders built in — overlaid against the contract baseline and the incumbent's re-forecast.

| Method | Concept | Watch items |
| --- | --- | --- |
| Jack-up barge | Self-elevating deck alongside the workfront; tide and motion free once jacked; walk-to-work to the structure; doubles as logistics base. A couple of units reportedly in the region; modular options in various sizes. | Bathymetry/seabed unproven; jacking cycle times if used low-to-high as a working platform; relocation cadence along 5.7 km; GBRMPA position. |
| Floating modular pontoons | Spud-moored modular decks that clip to the structure (e.g. off the handrails), working the lower band around LAT for pile wrapping; quick to shift bent to bent; some systems convert to suspended pods. | Sea-state limits for fine work; containment over open water; connection details to corroded steel. |
| Suspended modular pods | Engineered enclosures hung on electric chain hoists, riding the tide and walked bent to bent; serviced from the water. Prefabricated clamshell encapsulation (Altona/Liberty precedent) closing around headstocks for blast and coat. | Hanging loads on corroded members; RPEQ + independent check; hoist/beam logistics ahead of the line. |
| Marine rope access | Boat-supported crews running ahead of the plant: survey/UT mark-up, pile prep and Denso jacket fitting on planned tides. Spec already permits rope access on piles. | No containment, so wrap/prep work only; daily tide and weather planning. |
| Hybrid (leading) | Pods for headstock blast/coat, rope teams for piles, jack-up and/or barge as the logistics backbone replacing the roadway; gallery wrapping banked as the wind-day fallback; incumbent-style scaffold retained only for the sheltered front end. | Interface management across systems; the integrated schedule is the test. |

Market intel so far: GGC bid the original tender (priced high) and knows the job; the local scaffold outfit — since absorbed by a multinational — had proposed modular hung traversing scaffolds; jack-up contacts are being canvassed for availability, size options and rates. Baseline for comparison stays the current scaffold method, costed from the executed contract.

# 7   What we want from you — early feedback

Gut-feel first, precision later. Anything you can give us against these by early next week shapes where we spend the remaining study hours:

- Jack-up practicality: in ~shallow nearshore water on a likely sand/mud seabed beside a jetty, what's your experience of jacking cycle times (low-to-high as a daily work platform vs park-and-stay), preload/leg penetration risk without survey data, and realistic relocation cadence along a 5.7 km alignment? At what point does a jack-up become a base camp rather than a workfront?

MC Response: JUB can be used as a daily platform, however working time will be significantly reduced to max 4hr window to allow for relocation and preloading activities.

General Cycle times below;

- Jack down to float ~2hrs

- Move ~ 1-2hrs

- Jack up and Preload ~ 3-4hrs (Preload depends on barge weight.)

Move Limitations: Calm waters (< 0.3m Swell and <5 Knots current, Slack water)

Location Limits: > 4m draft. Tug / crew vessel / access draft to be considered.

Survivability: Generally, Cyclone Cat 1. (Relocate to sheltered water) Can jack up above predicted wave heights.

All weather restrictions are dependent on stability book.

Current JUB access via Work Punts only as no berthing infrastructure for CTV on JUB’s. May need to look at fendering system to increase weather reliability.

Maximisation of JUB would be to use as base for equipment and personnel and could provide access to max 2 bents from one location.

Install HIAB cranes on JUB’s for stores and equipment transfers.

- Walk-to-work: practical gangway/W2W options from a small jack-up or moored barge onto a low jetty deck, and their sea-state limits?

MC Response: Block style pontoons could be used. (T-Dock or DockPro) Predominately for smooth waters only. Max wave height 0.6m. Slippery when wet, would need additional anti-slip flooring.

If possible, drive minibus to passing bay, use passing bay for over side Scaffold Stair Access to Waterline or fabricate cranable aluminium stair access tower.

Potential to use floating modular scaffold and winch up from water level. Power for winching needs to be considered.

- Pontoon work at LAT: modular spud pontoons clipping onto the structure for pile wrapping around the tidal band — real-world workability limits (Hs/wind), and what connection/mooring detail would you trust on corroded steel?

MC Response: Block style pontoons could be used or prefabricated pontoons. Predominately for smooth waters only. Max wave height 0.6m. High Risk Marine Fauna interaction also needs to be considered. Raked Pile configuration needs to be considered in design with fendering system.

- Marine logistics: crew boat ops from the tug harbour — transfer limits, vessel days, crew sizes; is a daily marine commute for 20-30 trades realistic here?

MC Response: CTV ideal embarking and disembarking. No local Tug harbour present. Possibility to use facilities in Herbert River. Local Boat Ramp. Suggest use 2 work punts with 8 – 10 Pax per vessel. Will need 1 for rescue purposes anyway.

Night moves: board accepts low-risk marine moves on the tide (Hay Point style). Which moves would you plan at night, and which never?

MC Response: Preparation works for marine move could commence in low light periods (Jack up / Jack down). Would ultimately aim for all JUB / Platform movements to be conducted on first light to last light basis.

- Weather operability: for this coast Mar-Nov, what percentage of workable days would you plan for marine-side blast/paint in enclosures vs open wrap work? Sanity-check our working assumption that enclosed pods materially beat scaffold-wrap in the SE trades.

MC Response:

- If working from fixed suspended platforms or JUB, estimate 80 – 90% uptime.

- Floating environment 60- 80% uptime.

- Intertidal works would be reduced to 40 -50% due to tidal influence.

SE trade wind predominately during June – October exceeding 20 knots regularly influencing wind and swell in shallow waters. Ship berthing may offer some shelter from swell break but unlikely due to the predominant wind / swell direction being SE.

- Production rate: the target is ~4 bents/week across parallel fronts (6-8 bents in work at once) to clear ~227 bents in the 2027 and 2028 seasons. From your delivery experience, what would you resource to hit that, and where's the first bottleneck?

MC Response: Need to refine bents timing as bracing bents will exhibit 300% increase in intertidal works.

Agree with at least 4 separate bents being executed at once. Suggest 5 access fronts available to allow for constant cycling of platforms.

Work front breakdown would be as follows;

- Crew 1 – Preparation and blasting (3 Pax)

- Crew 2 – Repairs – Boilermakers – NDT inspections. (5 Pax)

- Crew 3 – Post repair blast and paint – final QA (3 Pax)

- Crew 4 – Installation of Denso System (3 Pax)

- Crew 5 – Coxswains / Scaff / Rigger / T/A’s for platform installation and relocation. (4-5 Pax)

- JUB – 1 x Bargemaster per barge QLD maritime requirement.

- Cost sanity: the owner's line is 'it can't cost 10x'. Rough order: what does a small jack-up or modular pontoon spread + crew boat cost per month in this market, and does the trade against ~$9M of scaffold access (plus 3+ years of prelims) feel winnable?

MC Response:

- CTV Crewed - $30 – 40k / month

- 2 x Work Punts Manned - $10k each per month

- JUB Manned (SeaLift 6) - $ 32k / month

- MultiCat Crewed - $60k month (not 100% sure if necessary, could use beetle barge and work punts. Depends on Ports requirements for JUB Moves.)

Total Marine monthly costs - $120 – 150k per month

Total Marine project cost - $3.15m

Note: considered Dec-27 – Mar-28 on full hire rates. CA to be done on demobe vs Standby rates.

- What are we missing? Red flags, better methods, contractors or equipment we should be talking to (we have GGC and the jack-up owners on the list), permits or marine assurance steps that bite earlier than people expect.

- MC Response:

- Environmental risk assessment for marine activities considering protected Dugong Habitat. Seagrass survey, potential vessel strike, vessel movement frequency.

- BIMCO’s and other marine insurances.

- GBRMPA permits.

- Local berthing access.

- Local accommodation accessibility (Tourism season similar to works window)

- Potential for use of dry ice blasting to reduce waste volume of coal tar and blasting media.

- Cyclone moorings or demobe facility.

- Port of Townsville charges (Berthing / Sullage disposal / Water / Diesel)

Summary:

- Establishing additional work fronts are a direct solve for acceleration.

- Establishing Cribbing facilities nearby to workfront (on JUB) will also increase productivity.

- Suggest revisit risk assessment for night works. Low risk tasks such as welding and paint and blast from platforms not impacted by tide and swell can be completed safely.

- Other considerations may need to come from methodology. ( i.e Paint recoat specs 14hrs between coats)

- Resequencing of integrity risk level to be addressed. Starting from high risk to lowest risk.

- Ultimately to achieve desired timeframe significant additional investment will be required.

Reference material available when you want it: the executed contract scope and spec, the contract program and the incumbent's re-forecast, our working session pack for the client (17 slides), site photos and the shipping history once STL sends them through. Shout and we'll share.

Contact:  Jed van Iersel  .  jed@enduradecom.com  .  0415 963 003     |     Shaun Kurien (Senior Consultant)     |     Strictly commercial in confidence — live contract dispute; do not distribute.